## SampleProjects
Parcel ID | Unique ID | Municipality | Address | City | Zipcode | County | State | Owner | Owner 2 | Mailing Address | Mail Line | Mail City | Mail State | Mail Zip | Sale Date | Sale Price | Land Value | Total Parcel Value | Deeded Acreage | Paces Calculated Acreage | Zoning Code | Zoning Description | Type | Latitude | Longitude | Alternate Parcel ID 1 | Parcel URL | Site ID | Site URL | Site Notes | Site Rating | Energy Community | Folder Name | Is Manually added | Is New from Latest Refresh | Latest Refresh Time | Greenfield Score | Buildable Shape Score | Distance to Closest Three Phase Line | Update Time of Closest Three Phase Line | Utility of Closest Three Phase Line | Substation Name connected to Closest Three Phase Line | Name of Closest Three Phase Line | Voltage (kV) of Closest Three Phase Line | Line Max Capacity of Closest Three Phase Line | Anti Islanding Capacity of Closest Three Phase Line | Load Zone of Closest Three Phase Line | Sub Installed DG of Closest Three Phase Line | Sub Queued DG of Closest Three Phase Line | Sub DG Change Since Last Refresh of Closest Three Phase Line | Previous Peak MW of Closest Three Phase Line | Thermal Capacity MVA of Closest Three Phase Line | Estimated 3v0 Protection MW of Closest Three Phase Line | Feeder Installed DG of Closest Three Phase Line | Feeder Queued DG of Closest Three Phase Line | Feeder DG Change Since Last Refresh of Closest Three Phase Line | Utility Last DG Refresh Time of Closest Three Phase Line | Connected Sub Capacity of Closest Three Phase Line | Substation Bank Name of Closest Three Phase Line | Alt Name of Closest Three Phase Line | Type of Closest Three Phase Line | Feeder Operating MW (Queue Data) of Closest Three Phase Line | Feeder Planned MW (Queue Data) of Closest Three Phase Line | Feeder Cancelled MW (Queue Data) of Closest Three Phase Line | Feeder Operating Project Count (Queue Data) of Closest Three Phase Line | Feeder Planned Project Count (Queue Data) of Closest Three Phase Line | Feeder Cancelled Project Count (Queue Data) of Closest Three Phase Line | Filter Criteria of Closest Three Phase Line
68111-00-838721 | bd56b604-996e-4449-9811-95ecfd480285 | Arcadia | 1545 Sleight Rd | Newark | 14513 | Wayne | NY | Graybill Real Estate Llc |  | 513 W UNION ST, , NEWARK, NY, 14513 | 513 W Union St | Newark | NY | 14513 |  |  | 61300 | 127500 | 70.29 | 68.4977 | A | Agriculture | Site | 43.0654 | -77.0769 | 54208906811100008387210000 | https://app.paces.ai/parcel?sourceId=bd56b604-996e-4449-9811-95ecfd480285&fips=36117 | 3533437 | https://app.paces.ai/site?siteId=3533437 | Will need to mitigate wetlands risk but overall great on POI, so close to sub - but is it big enough / are there two separate sites on the same parcel? | 4 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 50.54 | 0.53541 | 0.009 | 2025-03-11 | nyseg+rg&e | Sleight Rd | 4207947 | 34.5 | 10 | 0.16 | C | 3.23 | 42.31 | 3.03 |  | 10 |  | 3.08 | 22.34 | 3 | 2025-03-08 |  | 42079-NONE | 4207947 / 200545807 | O | 3.0937 | 31.4526 | 13.0906 | 10 | 6 | 6 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
68113-00-690342 | 9cc17482-815c-4895-9c6b-55244d10a27c | Arcadia | 694 Route 88 North | Arcadia | 14513 | Wayne | NY | Eckert, Charles D | Conklin, Eleanor E | 5192 ECKERT RD, , NEWARK, NY, 14513 | 5192 Eckert Rd | Newark | NY | 14513 | 2012-03-20 | 110000 | 75000 | 117344 | 68.77 | 67.0909 | A | Agriculture | Site | 43.1095 | -77.0824 | 54208906811300006903420000 | https://app.paces.ai/parcel?sourceId=9cc17482-815c-4895-9c6b-55244d10a27c&fips=36117 | 16589065 | https://app.paces.ai/site?siteId=16589065 | Good land and POI, wetland consideration | 5 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 75.15 | 0.84882 | 0.001 | 2025-03-11 | nyseg+rg&e | Sleight Rd | 4207947 | 34.5 | 10 | 0.16 | C | 3.23 | 42.31 | 3.03 |  | 10 |  | 3.08 | 22.34 | 3 | 2025-03-08 |  | 42079-NONE | 4207947 / 200543064 | O | 3.0937 | 31.4526 | 13.0906 | 10 | 6 | 6 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
68113-00-916923 | 80cc9b8f-7cfe-42aa-9713-2ccf0015b9f2 | Arcadia | Route 88 North | Arcadia | 14489 | Wayne | NY | Mdw Properties Llc |  | 4729 EDDY RIDGE RD, , MARION, NY, 14505 | 4729 Eddy Ridge Rd | Marion | NY | 14505 |  |  | 97500 | 153906 | 78.1 | 77.9524 | A | Agriculture | Site | 43.1253 | -77.0734 | 54208906811300009169230000 | https://app.paces.ai/parcel?sourceId=80cc9b8f-7cfe-42aa-9713-2ccf0015b9f2&fips=36117 | 16589098 | https://app.paces.ai/site?siteId=16589098 |  | 4 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 67.79 | 0.65061 | 0.015 | 2025-03-11 | nyseg+rg&e | Sleight Rd | 4207947 | 7.2 | 1.8 | 0.16 | C | 3.23 | 42.31 | 3.03 |  | 1.8 |  | 3.08 | 22.34 | 3 | 2025-03-08 |  | 42079-NONE | 4207947 / 200542861 | O | 3.0937 | 31.4526 | 13.0906 | 10 | 6 | 6 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
67111-00-696392 | 0d607f20-a7dc-4d3c-a829-42a10a2926aa | Arcadia | 5601 Stuart Ave | Newark | 14513-9726 | Wayne | NY | Schram, Kurtis |  | 5601 STUART AVE, , NEWARK, NY, 14513 | 5601 Stuart Ave | Newark | NY | 14513 |  |  | 81860 | 341188 | 62.8 | 61.8006 | A | Agriculture | Site | 43.056 | -77.1193 | 54208906711100006963920000 | https://app.paces.ai/parcel?sourceId=0d607f20-a7dc-4d3c-a829-42a10a2926aa&fips=36117 | 16589314 | https://app.paces.ai/site?siteId=16589314 | High permitting risk but otherwise pretty workable | 3 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 70.54 | 0.91486 | 0.121 | 2025-03-11 | nyseg+rg&e | Van Buren St | 4200405 | 12.5 | 0.1 | 0.55 | C | 9.07 | 0 | 9 | 10.43 | 0.1 | 1.05 | 9.02 | 0 | 8.98 | 2025-03-08 | 10.5 | 42004T2 | 4200405 / 200971486 | U | 9.0193 | 0 | 0 | 9 | 0 | 0 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
67111-00-906382 | 52986e38-f30b-42fa-be30-d316c3934107 | Arcadia | 5647 Stuart Ave | Newark | 14513-9726 | Wayne | NY | Pettine, Jamie A | Pettine, Philip J | 5647 STUART AVE, , NEWARK, NY, 14513 | 5647 Stuart Ave | Newark | NY | 14513 |  |  | 72200 | 259219 | 59.3 | 58.8719 | A | Agriculture | Site | 43.0555 | -77.1106 | 54208906711100009063820000 | https://app.paces.ai/parcel?sourceId=52986e38-f30b-42fa-be30-d316c3934107&fips=36117 | 16589316 | https://app.paces.ai/site?siteId=16589316 | City expanding, might not love this site | 3 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 61.94 | 0.65257 | 0.063 | 2025-03-11 | nyseg+rg&e | Van Buren St | 4200405 | 12.5 | 2 | 0.55 | C | 9.07 | 0 | 9 | 10.43 | 2 | 1.05 | 9.02 | 0 | 8.98 | 2025-03-08 | 10.5 | 42004T2 | 4200405 / 312159598 | U | 9.0193 | 0 | 0 | 9 | 0 | 0 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
67110-00-341957 | ba921b3d-79ad-4834-bd65-1a4916f6963c | Arcadia | Bailey Rd | Arcadia | 14513 | Wayne | NY | Ev Land Holding Llc |  | 14 PELIS RD, , NEWARK, NY, 14513 | 14 Pelis Rd | Newark | NY | 14513 |  |  | 68600 | 107188 | 57.89 | 57.9546 | A | Agriculture | Site | 43.0431 | -77.1323 | 54208906711000003419570000 | https://app.paces.ai/parcel?sourceId=ba921b3d-79ad-4834-bd65-1a4916f6963c&fips=36117 | 16589318 | https://app.paces.ai/site?siteId=16589318 | Good land, no environmental red flag, challenging POI | 5 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 70.29 | 0.90388 | 0.105 | 2025-03-11 | nyseg+rg&e | Van Buren St | 4200405 | 12.5 | 4.9 | 0.12 | C | 9.07 | 0 | 9 | 10.43 | 4.9 | 1.05 | 9.02 | 0 | 8.98 | 2025-03-08 | 10.5 | 42004T2 | 4200405 / 200557051 | O | 9.0193 | 0 | 0 | 9 | 0 | 0 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
67110-16-977279 | e13b44cc-35f9-44ca-b05b-da7ee04c0dbb | Arcadia | Peirson Ave | Newark | 14513 | Wayne | NY | El-Vi Farms, Llc |  | 14 PELIS RD, , NEWARK, NY, 14513 | 14 Pelis Rd | Newark | NY | 14513 | 2022-10-19 | 550000 | 80000 | 125000 | 78.9 | 80.8424 | A | Agriculture | Site | 43.0258 | -77.1087 | 54200106711000169772790000 | https://app.paces.ai/parcel?sourceId=e13b44cc-35f9-44ca-b05b-da7ee04c0dbb&fips=36117 | 16589670 | https://app.paces.ai/site?siteId=16589670 | Abutter risk? Across the street from tons of fancy suburban homes | 3 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 89.26 | 0.95192 | 0 | 2025-03-11 | nyseg+rg&e | Van Buren St | 4200404 | 12.5 | 1.6 | 0.48 | C | 9.07 | 0 | 9 | 10.43 | 2.2 | 1.05 | 0.05 | 0 | 0.02 | 2025-03-08 | 10.5 | 42004T2 | 4200404 / 200546341 | O | 0.05328 | 0 | 3.5 | 5 | 0 | 2 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
68112-00-532127 | 215e9e4d-58ac-49f8-b4fd-423df2369b15 | Arcadia | 1803 Route 88 North | Arcadia | 14513 | Wayne | NY | Jorgensen, Chad E | Jorgensen, Kelly A | 1803 ROUTE 88 NORTH, , NEWARK, NY, 14513 | 1803 Route 88 North | Newark | NY | 14513 | 2022-04-02 | 310000 | 83300 | 286094 | 60.22 | 63.3034 | A | Agriculture | Site | 43.0763 | -77.088 | 54208906811200005321270000 | https://app.paces.ai/parcel?sourceId=215e9e4d-58ac-49f8-b4fd-423df2369b15&fips=36117 | 16589714 | https://app.paces.ai/site?siteId=16589714 |  | 3 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 55.38 | 0.55051 | 0.012 | 2025-03-11 | nyseg+rg&e | Sleight Rd | 4207947 | 34.5 | 10 | 0.16 | C | 3.23 | 42.31 | 3.03 |  | 10 |  | 3.08 | 22.34 | 3 | 2025-03-08 |  | 42079-NONE | 4207947 / 200544629 | O | 3.0937 | 31.4526 | 13.0906 | 10 | 6 | 6 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
69112-00-071046 | 04421fad-bd9d-4cdd-b868-8719119d57e7 | Arcadia | 1759 Van Auken Rd | Newark | 14513-9220 | Wayne | NY | Dewilde, Albert J | Dewilde, Virginia L | 1881 VANAUKEN RD, , NEWARK, NY, 14513-0171 | 1881 Vanauken Rd | Newark | NY | 14513-0171 |  |  | 96000 | 185625 | 75.41 | 74.9909 | A | Agriculture | Site | 43.0741 | -77.0682 | 54208906911200000710460000 | https://app.paces.ai/parcel?sourceId=04421fad-bd9d-4cdd-b868-8719119d57e7&fips=36117 | 16589721 | https://app.paces.ai/site?siteId=16589721 | POI easement challenge, no env risk | 4 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 71.31 | 0.93718 | 0.217 | 2025-03-11 | nyseg+rg&e | Sleight Rd | 4207947 | 34.5 | 10 | 0.16 | C | 3.23 | 42.31 | 3.03 |  | 10 |  | 3.08 | 22.34 | 3 | 2025-03-08 |  | 42079-NONE | 4207947 / 200545792 | O | 3.0937 | 31.4526 | 13.0906 | 10 | 6 | 6 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e
68109-00-626896 | 3be1fe46-5458-4e38-92f8-10078d44157c | Arcadia | 109 Vienna Rd | Newark | 14513 | Wayne | NY | Nys Division Military & Naval |  | 109 VIENNA RD, , NEWARK, NY, 14513 | 109 Vienna Rd | Newark | NY | 14513 |  |  | 237000 | 385938 | 99.88 | 99.8625 | R | Residential Zone | Site | 43.015 | -77.084 | 54208906810900006268960000 | https://app.paces.ai/parcel?sourceId=3be1fe46-5458-4e38-92f8-10078d44157c&fips=36117 | 16589753 | https://app.paces.ai/site?siteId=16589753 | Tons of land to work with, POI is tough but manageable | 5 | No energy community | Whitepaper | TRUE | TRUE | 03/13/2025 18:01:38 EST | 77.98 | 0.87411 | 0.252 | 2025-03-11 | nyseg+rg&e | Van Buren St | 4200403 | 12.5 | 4.9 | 0.08 | C | 0.32 | 21.5 | 0 | 14.37 | 4.9 | 1.53 | 0.09 | 5 | 0 | 2025-03-08 | 16.8 | 42004T1 | 4200403 / 312114821 | O | 0.0929 | 5 | 12.15 | 10 | 1 | 4 | all names, all voltage, no three phase line capacity capacity restriction, no dg in queue capacity restriction, no three phase line sub capacity capacity restriction, no capacity minus dg in queue capacity restriction, no dg total capacity restriction, no three phase line remaining capacity capacity restriction, no max charge capacity restriction, no max discharge capacity restriction, no small pv hosting capacity capacity restriction, no planned dg (queue data) capacity restriction, No applications in queue restriction, no three phase line capacity minus planned dg (queue data) capacity restriction, no three phase line remaining capacity (queue data) capacity restriction, no Connected Sub Capacity - Sub Queued DG capacity restriction, all connected sub names, DER priority: unknown, no net daytime min load capacity restriction, utilities: nyseg+rg&e

## CapacityArchetype
Risk Category | Responsible Party | Counterparty | Task Type | Task | Description | Proof Point | Budget | High Budget | Min Time (days) | Median Time (days) | Max Time (days) | Risk | Type of Spend | Status | Completion Time Range Start | Completion Time Range End | Blocked by
Site Control |  | Property Owner |  | Letter of Intent | Sign LOI with landowner |  | 0 | 0 |  | 30 |  | 4
Interconnection |  | Utility | Relationship Building | Preapplication (Informal Request) | Request electric system information, give utility contact a call |  | 0 | 0 |  | 28 |  | 2
Interconnection |  | Utility | Submission/Coordination | Preapplication (Formal Request) | Nonrefundable fee for preapplication report |  | 750 | 750 |  | 84 |  | 3
Design | Developer |  | Research | Initial Concept Plan | High level layout of project with current understanding of site restrictions (all desktop), single line diagram |  | 1000 | 1000 |  | 14 |  | 2 | Labor
Interconnection |  | Utility | Submission/Coordination | Standard Interconnection Application | Submit filled-out application form |  | 750 | 750 | 7 | 15 | 30 | 1
Interconnection |  | Utility | Relationship Building | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. |  | 0 | 0 |  | 5 |  | 20 | Bond
Milestone
Permitting | Developer | Code Enforcement Officer | Relationship Building | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | Record of email exchange and phone call | 0 | 0 |  | 7 |  | 2 | Labor
Interconnection |  | Utility | Submission/Coordination | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information |  | 0 | 0 |  | 84 |  | 1
Site Control |  | Property Owner |  | Preliminary Title Search | Preliminary title search for encumbrances, deed's of trusts, and other potential title issues |  | 0 | 0
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Preliminary Wetlands Assessment | Perform a site visit to confirm presence or absence of freshwater wetlands on project site, map out limits if observed |  | 2750 | 5000 |  | 28 |  | 2
Site Control |  | Property Owner |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord |  | 0 | 0 |  | 7 |  | 1
Interconnection |  | Utility | Report/Study | CESIR Deposit Payment |  |  | 45000 | 0 |  | 56 |  | 1
Interconnection | Utility | Developer | Report/Study | CESIR Study | Utility does the study |  | 0 | 0 |  | 28 |  | 3
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. |  | 12500 | 12500 |  | 56 |  | 4 |  |  | March | November |  | if near wetland, want to skip preliminary and do full report earlier or just do preliinary to see if full report is needed
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. |  | 5000 | 12500 |  | 28 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Environmental Site Assessment (ESA) Phase I |  |  | 4000 | 5500 |  | 56 |  | 4
Design | Civil Engineer/Consultant | Developer | Report/Study | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research |  | 13500 | 20000 |  | 28 |  | 1
Design | Civil Engineer/Consultant | Developer | Report/Study | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm |  | 26500 | 26500 |  | 56 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources |  | 5000 | 15000 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination | CESIR Study Review | Review cost determinations |  | 45000 | 45000 |  | 84 |  | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders |  | 0 | 0 |  | 84 |  | 2
Permitting | Developer | Town Residents | Relationship Building | Notify and obtain consent from abutters | Get signatures from all nearby property owners consenting to building the solar system |  | 0 | 0 |  | 28 |  | 4
Site Control |  | Property Owner |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence |  | 1000 | 1000 |  | 84 |  | 1
Site Control |  | Property Owner | Report/Study | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters |  | 1000 | 1000 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Planning Board | Report/Study | Prepare Site Plan Application Package | Landscaping Plan, Stormwater Management Plan, abutter consent, Site Plan Design |  | 25000 | 45 |  |  |  | 1
Site Control |  | Property Owner | Report/Study | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor |  | 3500 | 35000 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Town Board | Report/Study | Prepare Special Use Permit Application Package | Propert Maintenance Plan, Glare Study, Noise Study, Construction Plan, PILOT Agreement, Decomissioning Plan + Agreement, Visual Resource Assessment, SEQR |  | 14000 | 22000 |  |  |  | 1
Permitting | Developer | Town Residents | Relationship Building | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. |  | 0 | 0 |  | 28 |  | 5
Permitting | Developer | Planning Board | Submission/Coordination | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | Record of agreement (at office of Wayne County Clerk) | 180000 | 300000 |  |  |  | 1
Permitting | Developer | Town Board | Relationship Building | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. |  | 10000 | 12000 | 62 | 84 |  | 5
Permitting | Town Board | Developer | Submission/Coordination | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. |  | 0 | 0 |  | 84 |  | 10
Interconnection |  | Utility | Submission/Coordination | NY Standardized Interconnection Contract (IA) | Come to terms on exact costs of upgrade + 25% payment of total cost quoted |  | 130000 | 0 |  | 7 |  | 1
526250
Site plan

## DesignArchetype
Risk Category | Responsible Party | Counterparty | Task Type | Task | Description | Proof Point | Budget | High Budget | Min Time (days) | Median Time (days) | Max Time (days) | Standard Risk | Type of Spend | Status | Completion Time Range Start | Completion Time Range End | Blocked by
Site Control |  | Property Owner |  | Letter of Intent | Sign LOI with landowner |  | 0 | 0 |  | 30 |  | 4
Design | Developer |  | Research | Initial Concept Plan | High level layout of project with current understanding of site restrictions (all desktop), single line diagram |  | 1000 | 1000 |  | 14 |  | 20 | Labor
Milestone
Interconnection |  | Utility | Relationship Building | Preapplication (Informal Request) | Request electric system information, give utility contact a call |  | 0 | 0 |  | 28 |  | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | Record of email exchange and phone call | 0 | 0 |  | 7 |  | 2 | Labor
Interconnection |  | Utility | Submission/Coordination | Preapplication (Formal Request) | Nonrefundable fee for preapplication report |  | 750 | 750 |  | 84 |  | 3
Interconnection |  | Utility | Submission/Coordination | Standard Interconnection Application | Submit filled-out application form |  | 750 | 750 | 7 | 15 | 30 | 1
Interconnection |  | Utility | Relationship Building | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. |  | 0 | 0 |  | 5 |  |  | Bond
Interconnection |  | Utility | Submission/Coordination | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information |  | 0 | 0 |  | 84 |  | 1
Site Control |  | Property Owner |  | Preliminary Title Search | Preliminary title search for encumbrances, deed's of trusts, and other potential title issues |  | 0 | 0
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Preliminary Wetlands Assessment | Perform a site visit to confirm presence or absence of freshwater wetlands on project site, map out limits if observed |  | 2750 | 5000 |  | 28 |  | 2
Site Control |  | Property Owner |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord |  | 0 | 0 |  | 7 |  | 1
Interconnection |  | Utility | Report/Study | CESIR Deposit Payment |  |  | 45000 | 0 |  | 56 |  | 1
Interconnection | Utility | Developer | Report/Study | CESIR Study | Utility does the study |  | 0 | 0 |  | 28 |  | 3
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. |  | 12500 | 12500 |  | 56 |  | 4 |  |  | March | November |  | if near wetland, want to skip preliminary and do full report earlier or just do preliinary to see if full report is needed
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. |  | 5000 | 12500 |  | 28 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Environmental Site Assessment (ESA) Phase I |  |  | 4000 | 5500 |  | 56 |  | 4
Design | Civil Engineer/Consultant | Developer | Report/Study | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research |  | 13500 | 20000 |  | 28 |  | 1
Design | Civil Engineer/Consultant | Developer | Report/Study | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm |  | 26500 | 26500 |  | 56 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources |  | 5000 | 15000 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination | CESIR Study Review | Review cost determinations |  | 45000 | 45000 |  | 84 |  | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders |  | 0 | 0 |  | 84 |  | 2
Permitting | Developer | Town Residents | Relationship Building | Notify and obtain consent from abutters | Get signatures from all nearby property owners consenting to building the solar system |  | 0 | 0 |  | 28 |  | 4
Site Control |  | Property Owner |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence |  | 1000 | 1000 |  | 84 |  | 1
Site Control |  | Property Owner | Report/Study | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters |  | 1000 | 1000 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Planning Board | Report/Study | Prepare Site Plan Application Package | Landscaping Plan, Stormwater Management Plan, abutter consent, Site Plan Design |  | 25000 | 45 |  |  |  | 1
Site Control |  | Property Owner | Report/Study | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor |  | 3500 | 35000 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Town Board | Report/Study | Prepare Special Use Permit Application Package | Propert Maintenance Plan, Glare Study, Noise Study, Construction Plan, PILOT Agreement, Decomissioning Plan + Agreement, Visual Resource Assessment, SEQR |  | 14000 | 22000 |  |  |  | 1
Permitting | Developer | Town Residents | Relationship Building | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. |  | 0 | 0 |  | 28 |  | 5
Permitting | Developer | Planning Board | Submission/Coordination | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | Record of agreement (at office of Wayne County Clerk) | 180000 | 300000 |  |  |  | 1
Permitting | Developer | Town Board | Relationship Building | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. |  | 10000 | 12000 | 62 | 84 |  | 5
Permitting | Town Board | Developer | Submission/Coordination | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. |  | 0 | 0 |  | 84 |  | 10
Interconnection |  | Utility | Submission/Coordination | NY Standardized Interconnection Contract (IA) | Come to terms on exact costs of upgrade + 25% payment of total cost quoted |  | 130000 | 0 |  | 7 |  | 1
526250
Site plan

## PermittingArchetype
Risk Category | Responsible Party | Counterparty | Task Type | Task | Description | Proof Point | Budget | High Budget | Min Time (days) | Median Time (days) | Max Time (days) | Standard Risk
Site Control |  | Property Owner |  | Letter of Intent | Sign LOI with landowner |  | 0 | 0 |  | 30 |  | 4
Permitting | Developer | Code Enforcement Officer | Relationship Building | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | Record of email exchange and phone call | 0 | 0 |  | 7 |  | 2
Permitting | Developer | Code Enforcement Officer | Relationship Building | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders |  | 0 | 0 |  | 84 |  | 2
Permitting | Developer | Town Residents | Relationship Building | Notify and obtain consent from abutters | Get signatures from all nearby property owners consenting to building the solar system |  | 0 | 0 |  | 28 |  | 4
Milestone
Interconnection |  | Utility | Relationship Building | Preapplication (Informal Request) | Request electric system information, give utility contact a call |  | 0 | 0 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination | Preapplication (Formal Request) | Nonrefundable fee for preapplication report |  | 750 | 750 |  | 84 |  | 3
Design | Developer |  | Research | Initial Concept Plan | High level layout of project with current understanding of site restrictions (all desktop), single line diagram |  | 1000 | 1000 |  | 14 |  | 2
Interconnection |  | Utility | Submission/Coordination | Standard Interconnection Application | Submit filled-out application form |  | 750 | 750 | 7 | 15 | 30 | 1
Interconnection |  | Utility | Relationship Building | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. |  | 0 | 0 |  | 5 |  | 5
Interconnection |  | Utility | Submission/Coordination | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information |  | 0 | 0 |  | 84 |  | 1
Site Control |  | Property Owner |  | Preliminary Title Search | Preliminary title search for encumbrances, deed's of trusts, and other potential title issues |  | 0 | 0 |  |  |  | 2
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Preliminary Wetlands Assessment | Perform a site visit to confirm presence or absence of freshwater wetlands on project site, map out limits if observed |  | 2750 | 5000 |  | 28 |  | 2
Site Control |  | Property Owner |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord |  | 0 | 0 |  | 7 |  | 1
Interconnection |  | Utility | Report/Study | CESIR Deposit Payment |  |  | 45000 | 0 |  | 56 |  | 1
Interconnection | Utility | Developer | Report/Study | CESIR Study | Utility does the study |  | 0 | 0 |  | 28 |  | 3
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. |  | 12500 | 12500 |  | 56 |  | 4
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. |  | 5000 | 12500 |  | 28 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Environmental Site Assessment (ESA) Phase I |  |  | 4000 | 5500 |  | 56 |  | 4
Design | Civil Engineer/Consultant | Developer | Report/Study | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research |  | 13500 | 20000 |  | 28 |  | 1
Design | Civil Engineer/Consultant | Developer | Report/Study | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm |  | 26500 | 26500 |  | 56 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources |  | 5000 | 15000 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination | CESIR Study Review | Review cost determinations |  | 45000 | 45000 |  | 84 |  | 1
Site Control |  | Property Owner |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence |  | 1000 | 1000 |  | 84 |  | 1
Site Control |  | Property Owner | Report/Study | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters |  | 1000 | 1000 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Planning Board | Report/Study | Prepare Site Plan Application Package | Landscaping Plan, Stormwater Management Plan, abutter consent, Site Plan Design |  | 25000 | 45 |  |  |  | 1
Site Control |  | Property Owner | Report/Study | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor |  | 3500 | 35000 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Town Board | Report/Study | Prepare Special Use Permit Application Package | Propert Maintenance Plan, Glare Study, Noise Study, Construction Plan, PILOT Agreement, Decomissioning Plan + Agreement, Visual Resource Assessment, SEQR |  | 14000 | 22000 |  |  |  | 1
Permitting | Developer | Town Residents | Relationship Building | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. |  | 0 | 0 |  | 28 |  | 5
Permitting | Developer | Planning Board | Submission/Coordination | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | Record of agreement (at office of Wayne County Clerk) | 180000 | 300000 |  |  |  | 1
Permitting | Developer | Town Board | Relationship Building | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. |  | 10000 | 12000 | 62 | 84 |  | 5
Permitting | Town Board | Developer | Submission/Coordination | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. |  | 0 | 0 |  | 84 |  | 10
Interconnection |  | Utility | Submission/Coordination | NY Standardized Interconnection Contract (IA) | Come to terms on exact costs of upgrade + 25% payment of total cost quoted |  | 130000 | 0 |  | 7 |  | 1
526250

## DesignInputs
Total Development Cost |  | kW DC | kW AC | Acres | ILR
| Size | 3000 | 2400 | 15 | 1.25
| Amount | $/wdc | $/wac | $/acre
Lease option | 0
Interconnection | 970000
IX Deposit | 0
Decomissioning Agreemnent | 180000 | 0.06
Title Policy | 0
Annual revenue | 210000 | 70
Budgeted DevEx | 180000 | 0.06
Budgeted IX | 970000 | 0.32333
Monthly Lease Rate | 15000 |  |  | 1000
OpEx | 15000
CapEx | 3000000 | 1000
Ultra Simplified Financial Model (DevEx and CapEx grouped together) | Year of Operation
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
DevEx | 180000
Budgeted IX | 970000
CapEx | 3000000
OpEx |  | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Annual Revenue |  | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000
Annual Cash Flow | -4150000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000
IRR | 1.279%
Development-focused Financial Model | Year Since Development Start
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
DevEx | 180000
Budgeted IX |  | 970000
CapEx |  |  | 3000000
OpEx |  |  |  | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Annual Revenue |  |  |  | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000
Annual Cash flow | -180000 | -970000 | -3000000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000
IRR | 1.246%
NTP
Probabilistic Financial Model
Probabilistic Financial Model | Year Since Development Start
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27
DevEx | 180000
Budgeted IX |  | 970000
CapEx |  |  | 3000000
OpEx |  |  |  | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000 | 15000
Annual Revenue |  |  |  | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000 | 210000
Annual Cash flow | -180000 | -970000 | -3000000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000 | 195000
Probability of Success (in current time period) | 0.7 | 0.9 | 0.98 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Cumulative Success Probability (up until current period) | 1 | 0.7 | 0.63 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174 | 0.6174
Expected Cash Flow | -180000 | -679000 | -1890000 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393 | 120393
Expected IRR | 0.689%

## EnviroArchetype
Risk Category | Responsible Party | Counterparty | Task Type | Task | Description | Proof Point | Budget | High Budget | Min Time (days) | Median Time (days) | Max Time (days) | Standard Risk
Site Control |  | Property Owner |  | Letter of Intent | Sign LOI with landowner |  | 0 | 0 |  | 30 |  | 4
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Preliminary Wetlands Assessment | Perform a site visit to confirm presence or absence of freshwater wetlands on project site, map out limits if observed |  | 2750 | 5000 |  | 28 |  | 2
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. |  | 12500 | 12500 |  | 56 |  | 4
Milestone
Interconnection |  | Utility | Relationship Building | Preapplication (Informal Request) | Request electric system information, give utility contact a call |  | 0 | 0 |  | 28 |  | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | Record of email exchange and phone call | 0 | 0 |  | 7 |  | 2
Interconnection |  | Utility | Submission/Coordination | Preapplication (Formal Request) | Nonrefundable fee for preapplication report |  | 750 | 750 |  | 84 |  | 3
Design | Developer |  | Research | Initial Concept Plan | High level layout of project with current understanding of site restrictions (all desktop), single line diagram |  | 1000 | 1000 |  | 14 |  | 2
Interconnection |  | Utility | Submission/Coordination | Standard Interconnection Application | Submit filled-out application form |  | 750 | 750 | 7 | 15 | 30 | 1
Interconnection |  | Utility | Relationship Building | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. |  | 0 | 0 |  | 5 |  | 5
Interconnection |  | Utility | Submission/Coordination | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information |  | 0 | 0 |  | 84 |  | 1
Site Control |  | Property Owner |  | Preliminary Title Search | Preliminary title search for encumbrances, deed's of trusts, and other potential title issues |  | 0 | 0 |  |  |  | 2
Site Control |  | Property Owner |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord |  | 0 | 0 |  | 7 |  | 1
Interconnection |  | Utility | Report/Study | CESIR Deposit Payment |  |  | 45000 | 0 |  | 56 |  | 1
Interconnection | Utility | Developer | Report/Study | CESIR Study | Utility does the study |  | 0 | 0 |  | 28 |  | 3
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. |  | 5000 | 12500 |  | 28 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Environmental Site Assessment (ESA) Phase I |  |  | 4000 | 5500 |  | 56 |  | 4
Design | Civil Engineer/Consultant | Developer | Report/Study | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research |  | 13500 | 20000 |  | 28 |  | 1
Design | Civil Engineer/Consultant | Developer | Report/Study | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm |  | 26500 | 26500 |  | 56 |  | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources |  | 5000 | 15000 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination | CESIR Study Review | Review cost determinations |  | 45000 | 45000 |  | 84 |  | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders |  | 0 | 0 |  | 84 |  | 2
Permitting | Developer | Town Residents | Relationship Building | Notify and obtain consent from abutters | Get signatures from all nearby property owners consenting to building the solar system |  | 0 | 0 |  | 28 |  | 4
Site Control |  | Property Owner |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence |  | 1000 | 1000 |  | 84 |  | 1
Site Control |  | Property Owner | Report/Study | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters |  | 1000 | 1000 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Planning Board | Report/Study | Prepare Site Plan Application Package | Landscaping Plan, Stormwater Management Plan, abutter consent, Site Plan Design |  | 25000 | 45 |  |  |  | 1
Site Control |  | Property Owner | Report/Study | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor |  | 3500 | 35000 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Town Board | Report/Study | Prepare Special Use Permit Application Package | Propert Maintenance Plan, Glare Study, Noise Study, Construction Plan, PILOT Agreement, Decomissioning Plan + Agreement, Visual Resource Assessment, SEQR |  | 14000 | 22000 |  |  |  | 1
Permitting | Developer | Town Residents | Relationship Building | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. |  | 0 | 0 |  | 28 |  | 5
Permitting | Developer | Planning Board | Submission/Coordination | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | Record of agreement (at office of Wayne County Clerk) | 180000 | 300000 |  |  |  | 1
Permitting | Developer | Town Board | Relationship Building | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. |  | 10000 | 12000 | 62 | 84 |  | 5
Permitting | Town Board | Developer | Submission/Coordination | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. |  | 0 | 0 |  | 84 |  | 10
Interconnection |  | Utility | Submission/Coordination | NY Standardized Interconnection Contract (IA) | Come to terms on exact costs of upgrade + 25% payment of total cost quoted |  | 130000 | 0 |  | 7 |  | 1
526250

## ArcadiaBaseModel
Risk Category | Responsible Party | Counterparty | Task Type | Task | Description | Low Budget | High Budget | Min Time (days) | Max Time (days) | Standard Risk | Depends On | Allow Parallel | Low Budget | High Budget
Site Control |  | Property Owner |  | Letter of Intent | Sign LOI with landowner | 0 | 0 | 30 | 60 | 4
Interconnection |  | Utility | Relationship Building | Preapplication (Informal Request) | Request electric system information, give utility contact a call | 0 | 0 | 5 | 9 | 1
Permitting | Developer | Code Enforcement Officer | Relationship Building | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | 0 | 0 | 5 | 9 | 5 | ["Letter of Intent"]
Interconnection |  | Utility | Submission/Coordination | Preapplication (Formal Request) | Nonrefundable fee for preapplication report | 500 | 1000 | 10 | 18 | 3
Site Control |  | Property Owner |  | Site Visit | Vist property to speak with landowner, form relationship | 200 | 500 | 3 | 5 | 2
Design | Developer |  | Research | Initial Concept Plan | High level layout of project with current understanding of site restrictions (all desktop), single line diagram | 1000 | 1000 | 7 | 14 | 1 | ["Preapplication (Formal Request)", "Site Visit"] |  | 100000 | 1500000
Interconnection |  | Utility | Submission/Coordination | Standard Interconnection Application | Submit filled-out application form. Requires Appendix H (landowner consent form). | 750 | 750 | 7 | 30 | 1 | ["Initial Concept Plan"]
Interconnection |  | Utility | Relationship Building | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. | 0 | 1000 | 14 | 28 | 10
Interconnection |  | Utility | Submission/Coordination | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information | 0 | 0 | 7 | 14 | 1
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Preliminary Wetlands Assessment | Desktop | 2750 | 5000 | 18 | 24 | 4 | ["Preliminary Review"]
Site Control |  | Property Owner | Report/Study | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor | 3500 | 3500 | 20 | 40 | 6
Site Control |  | Property Owner | Report/Study | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters | 1000 | 1000 | 20 | 40 | 3
Site Control |  | Property Owner |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord | 2000 | 3000 | 30 | 180 | 12
Interconnection |  | Utility | Report/Study | CESIR Payment | Submit payment. Have 14 days after app is submitted + invoice received to determine whether to spend money. | 15000 | 25000 | 1 | 14 | 1
Interconnection | Utility | Developer | Report/Study | CESIR Study | Utility does the study | 0 | 0 | 80 | 96 | 3
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. | 10000 | 12500 | 110 | 130 | 10 | ["Preliminary Wetlands Assessment"] | TRUE
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. | 5000 | 15000 | 30 | 120 | 6 | ["Preliminary Wetlands Assessment"] | TRUE
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Environmental Site Assessment (ESA) Phase I |  | 4000 | 5500 | 30 | 40 | 3 | ["Preliminary Wetlands Assessment"] | TRUE | 0 | 250000
Design | Civil Engineer/Consultant | Developer | Report/Study | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research | 17000 | 25000 | 60 | 90 | 3 | ["Preliminary Wetlands Assessment"] | TRUE
Environmental | Civil Engineer/Consultant | Developer | Report/Study | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources. SHPO analysis. | 5000 | 15000 | 30 | 120 | 6 | ["Preliminary Wetlands Assessment"] | TRUE
Design | Civil Engineer/Consultant | Developer | Report/Study | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm | 26500 | 26500 | 60 | 90 | 3 | ["Preliminary Wetlands Assessment"] | TRUE | 50000 | 500000 | steel and concerete is expensive
Interconnection |  | Utility | Submission/Coordination | CESIR Study Review | Review cost determinations | 0 | 0 | 14 | 90 | 15 |  |  | 250000 | 2000000
Interconnection |  |  |  | NY Standardized Interconnection Contract (IA) | Come to terms on exact costs of upgrade and sign agreement | 0 | 0 | 5 | 14 | 5
Permitting | Developer | Code Enforcement Officer | Relationship Building | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders | 0 | 0 | 7 | 7 | 5
Site Control |  | Property Owner |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence | 1000 | 1000 | 7 | 7 | 1
Permitting | Developer | Planning Board | Submission/Coordination | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | 1000 | 3000 | 7 | 7 | 1
Permitting | Civil Engineer/Consultant | Planning Board | Report/Study | Prepare Site Plan + Special Use Permit Application Package | Landscaping Plan, Stormwater Management Plan, abutter consent, Site Plan Design for site plan - Property Maintenance Plan, Glare Study, Noise Study, Construction Plan, PILOT Agreement, Decomissioning Plan + Agreement, Visual Resource Assessment, SEQR | 39000 | 77000 | 90 | 120 | 3 | ["Geotechnical Analysis", "Cultural Resource Survey"]
Permitting | Developer | Town Residents | Relationship Building | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. | 0 | 0 | 7 | 30 | 8
Permitting | Developer | Town Board | Relationship Building | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. | 0 | 10000 | 14 | 30 | 8
Permitting | Town Board | Developer | Submission/Coordination | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. | 0 | 0 | 14 | 30 | 10
Interconnection |  | Utility | Submission/Coordination | 25% Interconnection Deposit | Make 25% payment of total cost quoted in IA | 130000 | 130000 | 14 | 90 | 3

## New Simplified Financial Model
Risk Category | Financing Risk | DevEx | Increase in CapEx | Approval Risk | Go/No-Go Probability |  | System Overview | [6 empty] | Cost Low Bound | Cost Upper Bound | CapEx Low Bound | CapEx Upper Bound
Site Control | Low | 7700 | 0 | 5 | 0.85714 |  | Capacity Factor | 20% | Degradation Rate | 0.5% |  |  |  | 7700 | 9000 | 0 | 0
Permitting | Low | 40000 | 0 | 6 | 0.82143 |  | System Size (MW) | 3 | [5 empty] | 40000 | 90000 | 0 | 0
Interconnection | Low | 146250 | 250000 | 8 | 0.75 |  | AC system Size | 2.4 | [5 empty] | 146250 | 157750 | 250000 | 2000000
Design | Low | 44500 | 150000 | 2 | 0.96429 |  | Project Type | PPA | [5 empty] | 44500 | 52500 | 150000 | 2000000
Environmental | Low | 26750 | 0 | 6 | 0.82143 |  | Electricity Rate | 75 | [5 empty] | 26750 | 53000 | 0 | 250000
[7 empty] | Price Escalation | 1%
Total Dev Spend | 265200
Total Additional CapEx Spend | 400000
Base Case CapEx Spend | 2700000
Total CapEx Spend | 3100000
OpEx | 37500
Revenue | 315360
ITC | 30%
ITC Amount | 930000
Financial Model
Year Since Development Start
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Phase | Development | NTP and Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26 | Year 27 | Year 28 | Year 29 | Year 30
DevEx | 265200
CapEx |  | 3100000
OpEx |  |  | 37500 | 37875 | 38253.75 | 38636.2875 | 39022.6504 | 39412.8769 | 39807.0056 | 40205.0757 | 40607.1265 | 41013.1977 | 41423.3297 | 41837.563 | 42255.9386 | 42678.498 | 43105.283 | 43536.3358 | 43971.6992 | 44411.4162 | 44855.5303 | 45304.0856 | 45757.1265 | 46214.6978 | 46676.8447 | 47143.6132 | 47615.0493 | 48091.1998 | 48572.1118 | 49057.8329 | 49548.4113 | 50043.8954
Plant Degradation Factor |  |  | 1 | 99.5% | 99% | 98.5% | 98% | 97.5% | 97% | 96.5% | 96% | 95.5% | 95% | 94.5% | 94% | 93.5% | 93% | 92.5% | 92% | 91.5% | 91% | 90.5% | 90% | 89.5% | 89% | 88.5% | 88% | 87.5% | 87% | 86.5% | 86% | 85.5%
Electricity Generated (MWh) |  |  | 4204.8 | 4183.776 | 4162.752 | 4141.728 | 4120.704 | 4099.68 | 4078.656 | 4057.632 | 4036.608 | 4015.584 | 3994.56 | 3973.536 | 3952.512 | 3931.488 | 3910.464 | 3889.44 | 3868.416 | 3847.392 | 3826.368 | 3805.344 | 3784.32 | 3763.296 | 3742.272 | 3721.248 | 3700.224 | 3679.2 | 3658.176 | 3637.152 | 3616.128 | 3595.104
Electricity Rate ($/MWh) |  |  | 75 | 75.75 | 76.5075 | 77.2726 | 78.0453 | 78.8258 | 79.614 | 80.4102 | 81.2143 | 82.0264 | 82.8467 | 83.6751 | 84.5119 | 85.357 | 86.2106 | 87.0727 | 87.9434 | 88.8228 | 89.7111 | 90.6082 | 91.5143 | 92.4294 | 93.3537 | 94.2872 | 95.2301 | 96.1824 | 97.1442 | 98.1157 | 99.0968 | 100.0878
Benefits |  |  | 930000 |  | 0 | 0 | 0
Revenue |  |  | 315360 | 316921.032 | 318481.7486 | 320041.9875 | 321601.583 | 323160.3662 | 324718.1649 | 326274.8035 | 327830.1031 | 329383.8812 | 330935.9518 | 332486.1255 | 334034.209 | 335580.0056 | 337123.3147 | 338663.932 | 340201.6493 | 341736.2546 | 343267.5318 | 344795.2609 | 346319.2179 | 347839.1745 | 349354.8982 | 350866.1526 | 352372.6965 | 353874.2847 | 355370.6674 | 356861.5903 | 358346.7946 | 359826.0168
Cash Flow | -265200 | -3100000 | 1207860 | 279046.032 | 280227.9986 | 281405.7 | 282578.9326 | 283747.4893 | 284911.1592 | 286069.7278 | 287222.9766 | 288370.6834 | 289512.6221 | 290648.5625 | 291778.2704 | 292901.5076 | 294018.0317 | 295127.5962 | 296229.9502 | 297324.8384 | 298412.0015 | 299491.1753 | 300562.0914 | 301624.4767 | 302678.0535 | 303722.5394 | 304757.6472 | 305783.0849 | 306798.5556 | 307803.7574 | 308798.3834 | 309782.1215
Go/No-Go Probability | 41.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83%
Expected Cash Flow | -265200 | -1296646.254 | 505215.2079 | 116717.4168 | 117211.8015 | 117704.4022 | 118195.1337 | 118683.9094 | 119170.6411 | 119655.239 | 120137.6118 | 120617.6666 | 121095.3087 | 121570.4419 | 122042.9682 | 122512.788 | 122979.7998 | 123443.9007 | 123904.9856 | 124362.9478 | 124817.6787 | 125269.0679 | 125717.0032 | 126161.3703 | 126602.053 | 127038.9332 | 127471.8909 | 127900.8037 | 128325.5477 | 128745.9965 | 129162.0216 | 129573.4927
Expected IRR (for portfolio of projects) | 9.068%
Projects Reaching NTP | 41.83%
IRR of successful projects | 10.64%

## Financial Model-Full
Total Development Cost |  | kW DC | kW AC | Acres | ILR | Start Date | Duration (months)
| Size | 3000 | 2400 | 15 | 1.25 | [5 empty] | Development Start Date | NTP | COD
| Amount | $/wdc | $/wac | $/acre
Lease option | 52500 | 1.1667 | 1.4583 | 3500 |  | 2025-01-01 | 2
Interconnection | 970000 |  |  |  |  | 2025-08-01 | 36 |  |  |  | 2025-01-01 | 2027-04-13 | 2028-04-13
IX Deposit | 0 |  |  |  |  | 2025-06-01 | 2
Decomissioning Agreemnent | 180000 | 0.06 |  |  |  | 2025-03-01 | 1
Title Policy | 0 |  |  |  |  | 2025-01-01
Annual revenue | 210000 | 70
Budgeted DevEx | 232500 | 0.0775
Budgeted IX | 970000 | 0.32333
Monthly Lease Rate | 3125 |  |  | 208.3333 | 2500
OpEx (monthly) | 3125
CapEx | 3000000 | 1000
Probabilistic Financial Base Model
Base Case | Date
 | time axis 2025-01-01 to 2053-04-13
Process | Letter of Intent | Preapplication (Informal Request) | Initial AHJ Consultation | Preapplication (Formal Request) | Site Visit | Initial Concept Plan | Standard Interconnection Application | Preliminary Review | CESIR Study Application | Preliminary Wetlands Assessment | Lease Area and Easement Plan | Title Policy Report | Execute Lease Agreement | CESIR Payment | CESIR Study | Wetland Delineation Report | Ecological Assessment | Environmental Site Assessment (ESA) Phase I | Boundary & Topographic Property Survey | Cultural Resource Survey | Geotechnical Analysis | CESIR Study Review | NY Standardized Interconnection Contract (IA) | Pre-Application Meeting | Record Lease Memorandum | Decommissioning Agreement | Prepare Site Plan + Special Use Permit Application Package | Community Engagement Meeting | Public Hearing | Town Board Review | 25% Interconnection Deposit | NPC + Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26
Cost Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-03-30: Low; 2025-04-17: Low; 2025-05-07: Low; 2025-05-27: Low; 2025-06-26: Low; 2025-06-27: Low; 2025-09-15: Low; 2026-01-03: Low; 2026-02-02: Low; 2026-03-04: Low; 2026-05-03: Low; 2026-06-02: Low; 2026-08-01: Low; 2026-08-15: Low; 2026-08-20: Low; 2026-08-27: Low; 2026-09-03: Low; 2026-09-10: Low; 2026-12-09: Low; 2026-12-16: Low; 2026-12-30: Low; 2027-01-13: Low
Time Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-03-30: Low; 2025-04-17: Low; 2025-05-07: Low; 2025-05-27: Low; 2025-06-26: Low; 2025-06-27: Low; 2025-09-15: Low; 2026-01-03: Low; 2026-02-02: Low; 2026-03-04: Low; 2026-05-03: Low; 2026-06-02: Low; 2026-08-01: Low; 2026-08-15: Low; 2026-08-20: Low; 2026-08-27: Low; 2026-09-03: Low; 2026-09-10: Low; 2026-12-09: Low; 2026-12-16: Low; 2026-12-30: Low; 2027-01-13: Low
DevEx | 2025-01-01: 0; 2025-01-31: 0; 2025-02-05: 0; 2025-02-10: 500; 2025-02-20: 200; 2025-02-23: 1000; 2025-03-02: 750; 2025-03-09: 0; 2025-03-23: 0; 2025-03-30: 2750; 2025-04-17: 3500; 2025-05-07: 1000; 2025-05-27: 2000; 2025-06-26: 15000; 2025-06-27: 0; 2025-09-15: 10000; 2026-01-03: 5000; 2026-02-02: 4000; 2026-03-04: 17000; 2026-05-03: 5000; 2026-06-02: 26500; 2026-08-01: 0; 2026-08-15: 0; 2026-08-20: 0; 2026-08-27: 1000; 2026-09-03: 1000; 2026-09-10: 39000; 2026-12-09: 0; 2026-12-16: 0; 2026-12-30: 0; 2027-01-13: 130000
CapEx | 2027-04-13: 3000000
OpEx | 2028-04-13: 37500; 2029-04-13: 37500; 2030-04-13: 37500; 2031-04-13: 37500; 2032-04-13: 37500; 2033-04-13: 37500; 2034-04-13: 37500; 2035-04-13: 37500; 2036-04-13: 37500; 2037-04-13: 37500; 2038-04-13: 37500; 2039-04-13: 37500; 2040-04-13: 37500; 2041-04-13: 37500; 2042-04-13: 37500; 2043-04-13: 37500; 2044-04-13: 37500; 2045-04-13: 37500; 2046-04-13: 37500; 2047-04-13: 37500; 2048-04-13: 37500; 2049-04-13: 37500; 2050-04-13: 37500; 2051-04-13: 37500; 2052-04-13: 37500; 2053-04-13: 37500
Revenue | 2028-04-13: 210000; 2029-04-13: 210000; 2030-04-13: 210000; 2031-04-13: 210000; 2032-04-13: 210000; 2033-04-13: 210000; 2034-04-13: 210000; 2035-04-13: 210000; 2036-04-13: 210000; 2037-04-13: 210000; 2038-04-13: 210000; 2039-04-13: 210000; 2040-04-13: 210000; 2041-04-13: 210000; 2042-04-13: 210000; 2043-04-13: 210000; 2044-04-13: 210000; 2045-04-13: 210000; 2046-04-13: 210000; 2047-04-13: 210000; 2048-04-13: 210000; 2049-04-13: 210000; 2050-04-13: 210000; 2051-04-13: 210000; 2052-04-13: 210000; 2053-04-13: 210000
Cash Flow | 0 | 0 | 0 | -500 | -200 | -1000 | -750 | 0 | 0 | -2750 | -3500 | -1000 | -2000 | -15000 | 0 | -10000 | -5000 | -4000 | -17000 | -5000 | -26500 | 0 | 0 | 0 | -1000 | -1000 | -39000 | 0 | 0 | 0 | -130000 | -3000000 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500
Standard Risk Rating | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 10 | 1 | 4 | 6 | 3 | 12 | 1 | 3 | 10 | 6 | 3 | 3 | 6 | 3 | 15 | 5 | 5 | 1 | 1 | 3 | 8 | 8 | 10 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Go/No-Go Probability | 95.26% | 100% | 93.68% | 96.84% | 98.42% | 100% | 100% | 85.79% | 100% | 95.26% | 92.11% | 96.84% | 82.63% | 100% | 96.84% | 85.79% | 92.11% | 96.84% | 96.84% | 92.11% | 96.84% | 77.89% | 93.68% | 93.68% | 100% | 100% | 96.84% | 88.95% | 88.95% | 85.79% | 96.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 95.26% | 95.26% | 89.25% | 86.43% | 85.06% | 85.06% | 85.06% | 72.98% | 72.98% | 69.52% | 64.03% | 62.01% | 51.24% | 51.24% | 49.62% | 42.57% | 39.21% | 37.97% | 36.77% | 33.87% | 32.8% | 25.55% | 23.93% | 22.42% | 22.42% | 22.42% | 21.72% | 19.32% | 17.18% | 14.74% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27% | 14.27%
Expected Cash Flow | 0 | 0 | 0 | -446.2327 | -172.8565 | -850.6357 | -637.9768 | 0 | 0 | -2006.8287 | -2433.1598 | -640.3052 | -1240.1701 | -7685.7908 | 0 | -4962.0544 | -2128.4602 | -1568.3391 | -6454.9535 | -1838.5626 | -8975.0885 | 0 | 0 | 0 | -224.2322 | -224.2322 | -8745.0564 | 0 | 0 | 0 | -19160.4538 | -428201.2349 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571 | 24621.571
Risk | 2025-01-01: 14.27%; 2025-01-31: 14.98%; 2025-02-05: 14.98%; 2025-02-10: 15.99%; 2025-02-20: 16.51%; 2025-02-23: 16.78%; 2025-03-02: 16.78%; 2025-03-09: 16.78%; 2025-03-23: 19.56%; 2025-03-30: 19.56%; 2025-04-17: 20.53%; 2025-05-07: 22.29%; 2025-05-27: 23.02%; 2025-06-26: 27.86%; 2025-06-27: 27.86%; 2025-09-15: 28.77%; 2026-01-03: 33.53%; 2026-02-02: 36.4%; 2026-03-04: 37.59%; 2026-05-03: 38.82%; 2026-06-02: 42.14%; 2026-08-01: 43.52%; 2026-08-15: 55.87%; 2026-08-20: 59.63%; 2026-08-27: 63.65%; 2026-09-03: 63.65%; 2026-09-10: 63.65%; 2026-12-09: 65.73%; 2026-12-16: 73.9%; 2026-12-30: 83.08%; 2027-01-13: 96.84%; 2027-04-13: 100%
Expected IRR | 2025-01-01: 1.924%
Projects Reaching NTP | 2025-01-01: 14.27%
DevEx Costs | 2025-01-01: 265200
Capacity Archetype | 2025-01-01: Date
 | time axis 2025-01-01 to 2053-10-07
Process | Letter of Intent | Preapplication (Informal Request) | Initial AHJ Consultation | Preapplication (Formal Request) | Site Visit | Initial Concept Plan | Standard Interconnection Application | Preliminary Review | CESIR Study Application | Preliminary Wetlands Assessment | Lease Area and Easement Plan | Title Policy Report | Execute Lease Agreement | CESIR Payment | CESIR Study | Wetland Delineation Report | Ecological Assessment | Environmental Site Assessment (ESA) Phase I | Boundary & Topographic Property Survey | Cultural Resource Survey | Geotechnical Analysis | CESIR Study Review | NY Standardized Interconnection Contract (IA) | Pre-Application Meeting | Record Lease Memorandum | Decommissioning Agreement | Prepare Site Plan + Special Use Permit Application Package | Community Engagement Meeting | Public Hearing | Town Board Review | 25% Interconnection Deposit | NPC + Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26
Cost Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-04-06: High; 2025-04-13: Low; 2025-05-01: Low; 2025-05-21: Low; 2025-06-10: Low; 2025-12-07: High; 2025-12-21: High; 2026-03-11: Low; 2026-06-29: Low; 2026-07-29: Low; 2026-08-28: Low; 2026-10-27: Low; 2026-11-26: Low; 2027-01-25: Low; 2027-02-08: Low; 2027-02-13: Low; 2027-02-20: Low; 2027-02-27: Low; 2027-03-06: Low; 2027-06-04: Low; 2027-06-11: Low; 2027-06-25: Low; 2027-07-09: Low
Time Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-04-06: High; 2025-04-13: Low; 2025-05-01: Low; 2025-05-21: Low; 2025-06-10: Low; 2025-12-07: High; 2025-12-21: High; 2026-03-11: Low; 2026-06-29: Low; 2026-07-29: Low; 2026-08-28: Low; 2026-10-27: Low; 2026-11-26: Low; 2027-01-25: Low; 2027-02-08: Low; 2027-02-13: Low; 2027-02-20: Low; 2027-02-27: Low; 2027-03-06: Low; 2027-06-04: Low; 2027-06-11: Low; 2027-06-25: Low; 2027-07-09: Low
DevEx | 2025-01-01: 0; 2025-01-31: 0; 2025-02-05: 0; 2025-02-10: 500; 2025-02-20: 200; 2025-02-23: 1000; 2025-03-02: 750; 2025-03-09: 0; 2025-04-06: 0; 2025-04-13: 2750; 2025-05-01: 3500; 2025-05-21: 1000; 2025-06-10: 2000; 2025-12-07: 25000; 2025-12-21: 0; 2026-03-11: 10000; 2026-06-29: 5000; 2026-07-29: 4000; 2026-08-28: 17000; 2026-10-27: 5000; 2026-11-26: 26500; 2027-01-25: 0; 2027-02-08: 0; 2027-02-13: 0; 2027-02-20: 1000; 2027-02-27: 1000; 2027-03-06: 39000; 2027-06-04: 0; 2027-06-11: 0; 2027-06-25: 0; 2027-07-09: 130000
CapEx | 2027-10-07: 3000000
OpEx | 2028-10-07: 37500; 2029-10-07: 37500; 2030-10-07: 37500; 2031-10-07: 37500; 2032-10-07: 37500; 2033-10-07: 37500; 2034-10-07: 37500; 2035-10-07: 37500; 2036-10-07: 37500; 2037-10-07: 37500; 2038-10-07: 37500; 2039-10-07: 37500; 2040-10-07: 37500; 2041-10-07: 37500; 2042-10-07: 37500; 2043-10-07: 37500; 2044-10-07: 37500; 2045-10-07: 37500; 2046-10-07: 37500; 2047-10-07: 37500; 2048-10-07: 37500; 2049-10-07: 37500; 2050-10-07: 37500; 2051-10-07: 37500; 2052-10-07: 37500; 2053-10-07: 37500
Revenue | 2028-10-07: 210000; 2029-10-07: 210000; 2030-10-07: 210000; 2031-10-07: 210000; 2032-10-07: 210000; 2033-10-07: 210000; 2034-10-07: 210000; 2035-10-07: 210000; 2036-10-07: 210000; 2037-10-07: 210000; 2038-10-07: 210000; 2039-10-07: 210000; 2040-10-07: 210000; 2041-10-07: 210000; 2042-10-07: 210000; 2043-10-07: 210000; 2044-10-07: 210000; 2045-10-07: 210000; 2046-10-07: 210000; 2047-10-07: 210000; 2048-10-07: 210000; 2049-10-07: 210000; 2050-10-07: 210000; 2051-10-07: 210000; 2052-10-07: 210000; 2053-10-07: 210000
Cash Flow | 0 | 0 | 0 | -500 | -200 | -1000 | -750 | 0 | 0 | -2750 | -3500 | -1000 | -2000 | -25000 | 0 | -10000 | -5000 | -4000 | -17000 | -5000 | -26500 | 0 | 0 | 0 | -1000 | -1000 | -39000 | 0 | 0 | 0 | -130000 | -3000000 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500
Standard Risk Rating | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 20 | 1 | 4 | 6 | 3 | 12 | 1 | 3 | 10 | 6 | 3 | 3 | 6 | 3 | 20 | 5 | 5 | 1 | 1 | 3 | 8 | 8 | 10 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Go/No-Go Probability | 95.26% | 100% | 93.68% | 96.84% | 98.42% | 100% | 100% | 70% | 100% | 95.26% | 92.11% | 96.84% | 82.63% | 100% | 96.84% | 85.79% | 92.11% | 96.84% | 96.84% | 92.11% | 96.84% | 70% | 93.68% | 93.68% | 100% | 100% | 96.84% | 88.95% | 88.95% | 85.79% | 96.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 95.26% | 95.26% | 89.25% | 86.43% | 85.06% | 85.06% | 85.06% | 59.54% | 59.54% | 56.72% | 52.25% | 50.6% | 41.81% | 41.81% | 40.49% | 34.73% | 31.99% | 30.98% | 30% | 27.63% | 26.76% | 18.73% | 17.55% | 16.44% | 16.44% | 16.44% | 15.92% | 14.16% | 12.6% | 10.81% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47% | 10.47%
Expected Cash Flow | 0 | 0 | 0 | -446.2327 | -172.8565 | -850.6357 | -637.9768 | 0 | 0 | -1637.4737 | -1985.3389 | -522.4576 | -1011.9179 | -10452.0468 | 0 | -4048.7929 | -1736.719 | -1279.6877 | -5266.9253 | -1500.1769 | -7323.2317 | 0 | 0 | 0 | -164.419 | -164.419 | -6412.3405 | 0 | 0 | 0 | -14049.4639 | -313979.9222 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455 | 18053.8455
Expected IRR | 2025-01-01: 1.742%
Projects Reaching NTP | 2025-01-01: 10.47%
DevEx Costs | 2025-01-01: 275200
Permitting Archetype | 2025-01-01: Date
 | time axis 2025-01-01 to 2053-06-21
Process | Letter of Intent | Preapplication (Informal Request) | Initial AHJ Consultation | Preapplication (Formal Request) | Site Visit | Initial Concept Plan | Standard Interconnection Application | Preliminary Review | CESIR Study Application | Preliminary Wetlands Assessment | Lease Area and Easement Plan | Title Policy Report | Execute Lease Agreement | CESIR Payment | CESIR Study | Wetland Delineation Report | Ecological Assessment | Environmental Site Assessment (ESA) Phase I | Boundary & Topographic Property Survey | Cultural Resource Survey | Geotechnical Analysis | CESIR Study Review | NY Standardized Interconnection Contract (IA) | Pre-Application Meeting | Record Lease Memorandum | Decommissioning Agreement | Prepare Site Plan + Special Use Permit Application Package | Community Engagement Meeting | Public Hearing | Town Board Review | 25% Interconnection Deposit | NPC + Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26
Cost Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-03-30: Low; 2025-04-17: Low; 2025-05-07: Low; 2025-05-27: Low; 2025-06-26: Low; 2025-06-27: Low; 2025-09-15: Low; 2026-01-03: Low; 2026-02-02: Low; 2026-03-04: Low; 2026-05-03: Low; 2026-06-02: Low; 2026-08-01: Low; 2026-08-15: Low; 2026-08-20: Low; 2026-08-27: Low; 2026-09-03: Low; 2026-09-10: High; 2027-01-08: High; 2027-02-07: High; 2027-03-09: High; 2027-03-23: Low
Time Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-03-30: Low; 2025-04-17: Low; 2025-05-07: Low; 2025-05-27: Low; 2025-06-26: Low; 2025-06-27: Low; 2025-09-15: Low; 2026-01-03: Low; 2026-02-02: Low; 2026-03-04: Low; 2026-05-03: Low; 2026-06-02: Low; 2026-08-01: Low; 2026-08-15: Low; 2026-08-20: Low; 2026-08-27: Low; 2026-09-03: Low; 2026-09-10: High; 2027-01-08: High; 2027-02-07: High; 2027-03-09: High; 2027-03-23: Low
DevEx | 2025-01-01: 0; 2025-01-31: 0; 2025-02-05: 0; 2025-02-10: 500; 2025-02-20: 200; 2025-02-23: 1000; 2025-03-02: 750; 2025-03-09: 0; 2025-03-23: 0; 2025-03-30: 2750; 2025-04-17: 3500; 2025-05-07: 1000; 2025-05-27: 2000; 2025-06-26: 15000; 2025-06-27: 0; 2025-09-15: 10000; 2026-01-03: 5000; 2026-02-02: 4000; 2026-03-04: 17000; 2026-05-03: 5000; 2026-06-02: 26500; 2026-08-01: 0; 2026-08-15: 0; 2026-08-20: 0; 2026-08-27: 1000; 2026-09-03: 1000; 2026-09-10: 77000; 2027-01-08: 0; 2027-02-07: 10000; 2027-03-09: 0; 2027-03-23: 130000
CapEx | 2027-06-21: 3000000
OpEx | 2028-06-21: 37500; 2029-06-21: 37500; 2030-06-21: 37500; 2031-06-21: 37500; 2032-06-21: 37500; 2033-06-21: 37500; 2034-06-21: 37500; 2035-06-21: 37500; 2036-06-21: 37500; 2037-06-21: 37500; 2038-06-21: 37500; 2039-06-21: 37500; 2040-06-21: 37500; 2041-06-21: 37500; 2042-06-21: 37500; 2043-06-21: 37500; 2044-06-21: 37500; 2045-06-21: 37500; 2046-06-21: 37500; 2047-06-21: 37500; 2048-06-21: 37500; 2049-06-21: 37500; 2050-06-21: 37500; 2051-06-21: 37500; 2052-06-21: 37500; 2053-06-21: 37500
Revenue | 2028-06-21: 210000; 2029-06-21: 210000; 2030-06-21: 210000; 2031-06-21: 210000; 2032-06-21: 210000; 2033-06-21: 210000; 2034-06-21: 210000; 2035-06-21: 210000; 2036-06-21: 210000; 2037-06-21: 210000; 2038-06-21: 210000; 2039-06-21: 210000; 2040-06-21: 210000; 2041-06-21: 210000; 2042-06-21: 210000; 2043-06-21: 210000; 2044-06-21: 210000; 2045-06-21: 210000; 2046-06-21: 210000; 2047-06-21: 210000; 2048-06-21: 210000; 2049-06-21: 210000; 2050-06-21: 210000; 2051-06-21: 210000; 2052-06-21: 210000; 2053-06-21: 210000
Cash Flow | 0 | 0 | 0 | -500 | -200 | -1000 | -750 | 0 | 0 | -2750 | -3500 | -1000 | -2000 | -15000 | 0 | -10000 | -5000 | -4000 | -17000 | -5000 | -26500 | 0 | 0 | 0 | -1000 | -1000 | -77000 | 0 | -10000 | 0 | -130000 | -3000000 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500
Standard Risk Rating | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 10 | 1 | 4 | 6 | 3 | 12 | 1 | 3 | 10 | 6 | 3 | 3 | 6 | 3 | 15 | 5 | 5 | 1 | 1 | 3 | 10 | 10 | 12 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Go/No-Go Probability | 93.68% | 100% | 93.68% | 96.84% | 98.42% | 100% | 100% | 85.79% | 100% | 95.26% | 92.11% | 96.84% | 82.63% | 100% | 96.84% | 85.79% | 92.11% | 96.84% | 96.84% | 92.11% | 96.84% | 77.89% | 93.68% | 93.68% | 100% | 100% | 96.84% | 85.79% | 85.79% | 82.63% | 96.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 93.68% | 93.68% | 87.77% | 85% | 83.65% | 83.65% | 83.65% | 71.77% | 71.77% | 68.37% | 62.97% | 60.98% | 50.39% | 50.39% | 48.8% | 41.86% | 38.56% | 37.34% | 36.16% | 33.31% | 32.26% | 25.13% | 23.54% | 22.05% | 22.05% | 22.05% | 21.36% | 18.32% | 15.72% | 12.99% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58% | 12.58%
Expected Cash Flow | 0 | 0 | 0 | -438.8366 | -169.9914 | -836.5368 | -627.4026 | 0 | 0 | -1973.5663 | -2392.8311 | -629.6924 | -1219.6148 | -7558.402 | 0 | -4879.8104 | -2093.1818 | -1542.3445 | -6347.9653 | -1808.0892 | -8826.3301 | 0 | 0 | 0 | -220.5157 | -220.5157 | -16979.7057 | 0 | -1832.0514 | 0 | -16883.445 | -377314.2352 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685 | 21695.5685
Expected IRR | 2025-01-01: 1.64%
Projects Reaching NTP | 2025-01-01: 12.58%
DevEx Costs | 2025-01-01: 313200
Enviro Archetype | 2025-01-01: Date
 | time axis 2025-01-01 to 2053-09-23
Process | Letter of Intent | Preapplication (Informal Request) | Initial AHJ Consultation | Preapplication (Formal Request) | Site Visit | Initial Concept Plan | Standard Interconnection Application | Preliminary Review | CESIR Study Application | Preliminary Wetlands Assessment | Lease Area and Easement Plan | Title Policy Report | Execute Lease Agreement | CESIR Payment | CESIR Study | Wetland Delineation Report | Ecological Assessment | Environmental Site Assessment (ESA) Phase I | Boundary & Topographic Property Survey | Cultural Resource Survey | Geotechnical Analysis | CESIR Study Review | NY Standardized Interconnection Contract (IA) | Pre-Application Meeting | Record Lease Memorandum | Decommissioning Agreement | Prepare Site Plan + Special Use Permit Application Package | Community Engagement Meeting | Public Hearing | Town Board Review | 25% Interconnection Deposit | NPC + Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26
Cost Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-04-06: High; 2025-04-24: Low; 2025-05-14: Low; 2025-06-03: Low; 2025-07-03: Low; 2025-07-04: Low; 2025-10-08: High; 2026-02-15: High; 2026-06-15: High; 2026-07-15: Low; 2026-10-13: High; 2026-11-12: Low; 2027-01-11: Low; 2027-01-25: Low; 2027-01-30: Low; 2027-02-06: Low; 2027-02-13: Low; 2027-02-20: Low; 2027-05-21: Low; 2027-05-28: Low; 2027-06-11: Low; 2027-06-25: Low
Time Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-23: Low; 2025-03-02: Low; 2025-03-09: Low; 2025-03-23: Low; 2025-04-06: High; 2025-04-24: Low; 2025-05-14: Low; 2025-06-03: Low; 2025-07-03: Low; 2025-07-04: Low; 2025-10-08: High; 2026-02-15: High; 2026-06-15: High; 2026-07-15: Low; 2026-10-13: High; 2026-11-12: Low; 2027-01-11: Low; 2027-01-25: Low; 2027-01-30: Low; 2027-02-06: Low; 2027-02-13: Low; 2027-02-20: Low; 2027-05-21: Low; 2027-05-28: Low; 2027-06-11: Low; 2027-06-25: Low
DevEx | 2025-01-01: 0; 2025-01-31: 0; 2025-02-05: 0; 2025-02-10: 500; 2025-02-20: 200; 2025-02-23: 1000; 2025-03-02: 750; 2025-03-09: 0; 2025-03-23: 0; 2025-04-06: 5000; 2025-04-24: 3500; 2025-05-14: 1000; 2025-06-03: 2000; 2025-07-03: 15000; 2025-07-04: 0; 2025-10-08: 12500; 2026-02-15: 15000; 2026-06-15: 5500; 2026-07-15: 17000; 2026-10-13: 15000; 2026-11-12: 26500; 2027-01-11: 0; 2027-01-25: 0; 2027-01-30: 0; 2027-02-06: 1000; 2027-02-13: 1000; 2027-02-20: 39000; 2027-05-21: 0; 2027-05-28: 0; 2027-06-11: 0; 2027-06-25: 130000
CapEx | 2027-09-23: 3000000
OpEx | 2028-09-23: 37500; 2029-09-23: 37500; 2030-09-23: 37500; 2031-09-23: 37500; 2032-09-23: 37500; 2033-09-23: 37500; 2034-09-23: 37500; 2035-09-23: 37500; 2036-09-23: 37500; 2037-09-23: 37500; 2038-09-23: 37500; 2039-09-23: 37500; 2040-09-23: 37500; 2041-09-23: 37500; 2042-09-23: 37500; 2043-09-23: 37500; 2044-09-23: 37500; 2045-09-23: 37500; 2046-09-23: 37500; 2047-09-23: 37500; 2048-09-23: 37500; 2049-09-23: 37500; 2050-09-23: 37500; 2051-09-23: 37500; 2052-09-23: 37500; 2053-09-23: 37500
Revenue | 2028-09-23: 210000; 2029-09-23: 210000; 2030-09-23: 210000; 2031-09-23: 210000; 2032-09-23: 210000; 2033-09-23: 210000; 2034-09-23: 210000; 2035-09-23: 210000; 2036-09-23: 210000; 2037-09-23: 210000; 2038-09-23: 210000; 2039-09-23: 210000; 2040-09-23: 210000; 2041-09-23: 210000; 2042-09-23: 210000; 2043-09-23: 210000; 2044-09-23: 210000; 2045-09-23: 210000; 2046-09-23: 210000; 2047-09-23: 210000; 2048-09-23: 210000; 2049-09-23: 210000; 2050-09-23: 210000; 2051-09-23: 210000; 2052-09-23: 210000; 2053-09-23: 210000
Cash Flow | 0 | 0 | 0 | -500 | -200 | -1000 | -750 | 0 | 0 | -5000 | -3500 | -1000 | -2000 | -15000 | 0 | -12500 | -15000 | -5500 | -17000 | -15000 | -26500 | 0 | 0 | 0 | -1000 | -1000 | -39000 | 0 | 0 | 0 | -130000 | -3000000 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500
Standard Risk Rating | 4 | 1 | 5 | 3 | 2 | 1 | 1 | 10 | 1 | 5 | 6 | 3 | 12 | 1 | 3 | 12 | 10 | 5 | 3 | 8 | 3 | 15 | 5 | 5 | 1 | 1 | 3 | 8 | 8 | 10 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Go/No-Go Probability | 95.26% | 100% | 93.68% | 96.84% | 98.42% | 100% | 100% | 85.79% | 100% | 93.68% | 92.11% | 96.84% | 82.63% | 100% | 96.84% | 82.63% | 85.79% | 93.68% | 96.84% | 88.95% | 96.84% | 77.89% | 93.68% | 93.68% | 100% | 100% | 96.84% | 88.95% | 88.95% | 85.79% | 96.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 95.26% | 95.26% | 89.25% | 86.43% | 85.06% | 85.06% | 85.06% | 72.98% | 72.98% | 68.37% | 62.97% | 60.98% | 50.39% | 50.39% | 48.8% | 40.32% | 34.59% | 32.41% | 31.38% | 27.92% | 27.03% | 21.06% | 19.73% | 18.48% | 18.48% | 18.48% | 17.9% | 15.92% | 14.16% | 12.15% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76% | 11.76%
Expected Cash Flow | 0 | 0 | 0 | -446.2327 | -172.8565 | -850.6357 | -637.9768 | 0 | 0 | -3648.7794 | -2392.8311 | -629.6924 | -1219.6148 | -7558.402 | 0 | -6099.763 | -6048.3966 | -1902.5921 | -5509.3242 | -4707.6578 | -7397.63 | 0 | 0 | 0 | -184.8212 | -184.8212 | -7208.0282 | 0 | 0 | 0 | -15792.819 | -352940.7318 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921 | 20294.0921
Expected IRR | 2025-01-01: 1.634%
Projects Reaching NTP | 2025-01-01: 11.76%
DevEx Costs | 2025-01-01: -291450
Design Archetype | 2025-01-01: Date
 | time axis 2025-01-01 to 2053-07-24
Process | Letter of Intent | Preapplication (Informal Request) | Initial AHJ Consultation | Preapplication (Formal Request) | Site Visit | Initial Concept Plan | Standard Interconnection Application | Preliminary Review | CESIR Study Application | Preliminary Wetlands Assessment | Lease Area and Easement Plan | Title Policy Report | Execute Lease Agreement | CESIR Payment | CESIR Study | Wetland Delineation Report | Ecological Assessment | Environmental Site Assessment (ESA) Phase I | Boundary & Topographic Property Survey | Cultural Resource Survey | Geotechnical Analysis | CESIR Study Review | NY Standardized Interconnection Contract (IA) | Pre-Application Meeting | Record Lease Memorandum | Decommissioning Agreement | Prepare Site Plan + Special Use Permit Application Package | Community Engagement Meeting | Public Hearing | Town Board Review | 25% Interconnection Deposit | NPC + Construction | COD | Year 2 | Year 3 | Year 4 | Year 5 | Year 6 | Year 7 | Year 8 | Year 9 | Year 10 | Year 11 | Year 12 | Year 13 | Year 14 | Year 15 | Year 16 | Year 17 | Year 18 | Year 19 | Year 20 | Year 21 | Year 22 | Year 23 | Year 24 | Year 25 | Year 26
Cost Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-25: High; 2025-03-04: Low; 2025-03-11: Low; 2025-03-25: Low; 2025-04-01: Low; 2025-04-19: Low; 2025-05-09: Low; 2025-05-29: Low; 2025-06-28: Low; 2025-06-29: Low; 2025-09-17: Low; 2026-01-05: Low; 2026-02-04: Low; 2026-03-16: High; 2026-05-15: Low; 2026-09-12: High; 2026-11-11: Low; 2026-11-25: Low; 2026-11-30: Low; 2026-12-07: Low; 2026-12-14: Low; 2026-12-21: Low; 2027-03-21: Low; 2027-03-28: Low; 2027-04-11: Low; 2027-04-25: Low
Time Scenario | 2025-01-01: Low; 2025-01-31: Low; 2025-02-05: Low; 2025-02-10: Low; 2025-02-20: Low; 2025-02-25: High; 2025-03-04: Low; 2025-03-11: Low; 2025-03-25: Low; 2025-04-01: Low; 2025-04-19: Low; 2025-05-09: Low; 2025-05-29: Low; 2025-06-28: Low; 2025-06-29: Low; 2025-09-17: Low; 2026-01-05: Low; 2026-02-04: Low; 2026-03-16: High; 2026-05-15: Low; 2026-09-12: High; 2026-11-11: Low; 2026-11-25: Low; 2026-11-30: Low; 2026-12-07: Low; 2026-12-14: Low; 2026-12-21: Low; 2027-03-21: Low; 2027-03-28: Low; 2027-04-11: Low; 2027-04-25: Low
DevEx | 2025-01-01: 0; 2025-01-31: 0; 2025-02-05: 0; 2025-02-10: 500; 2025-02-20: 200; 2025-02-25: 1000; 2025-03-04: 750; 2025-03-11: 0; 2025-03-25: 0; 2025-04-01: 2750; 2025-04-19: 3500; 2025-05-09: 1000; 2025-05-29: 2000; 2025-06-28: 15000; 2025-06-29: 0; 2025-09-17: 10000; 2026-01-05: 5000; 2026-02-04: 4000; 2026-03-16: 25000; 2026-05-15: 5000; 2026-09-12: 26500; 2026-11-11: 0; 2026-11-25: 0; 2026-11-30: 0; 2026-12-07: 1000; 2026-12-14: 1000; 2026-12-21: 39000; 2027-03-21: 0; 2027-03-28: 0; 2027-04-11: 0; 2027-04-25: 130000
CapEx | 2027-07-24: 3000000
OpEx | 2028-07-24: 37500; 2029-07-24: 37500; 2030-07-24: 37500; 2031-07-24: 37500; 2032-07-24: 37500; 2033-07-24: 37500; 2034-07-24: 37500; 2035-07-24: 37500; 2036-07-24: 37500; 2037-07-24: 37500; 2038-07-24: 37500; 2039-07-24: 37500; 2040-07-24: 37500; 2041-07-24: 37500; 2042-07-24: 37500; 2043-07-24: 37500; 2044-07-24: 37500; 2045-07-24: 37500; 2046-07-24: 37500; 2047-07-24: 37500; 2048-07-24: 37500; 2049-07-24: 37500; 2050-07-24: 37500; 2051-07-24: 37500; 2052-07-24: 37500; 2053-07-24: 37500
Revenue | 2028-07-24: 210000; 2029-07-24: 210000; 2030-07-24: 210000; 2031-07-24: 210000; 2032-07-24: 210000; 2033-07-24: 210000; 2034-07-24: 210000; 2035-07-24: 210000; 2036-07-24: 210000; 2037-07-24: 210000; 2038-07-24: 210000; 2039-07-24: 210000; 2040-07-24: 210000; 2041-07-24: 210000; 2042-07-24: 210000; 2043-07-24: 210000; 2044-07-24: 210000; 2045-07-24: 210000; 2046-07-24: 210000; 2047-07-24: 210000; 2048-07-24: 210000; 2049-07-24: 210000; 2050-07-24: 210000; 2051-07-24: 210000; 2052-07-24: 210000; 2053-07-24: 210000
Cash Flow | 0 | 0 | 0 | -500 | -200 | -1000 | -750 | 0 | 0 | -2750 | -3500 | -1000 | -2000 | -15000 | 0 | -10000 | -5000 | -4000 | -25000 | -5000 | -26500 | 0 | 0 | 0 | -1000 | -1000 | -39000 | 0 | 0 | 0 | -130000 | -3000000 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500 | 172500
Standard Risk Rating | 4 | 1 | 5 | 3 | 2 | 10 | 1 | 10 | 1 | 4 | 6 | 3 | 12 | 1 | 3 | 10 | 6 | 3 | 5 | 6 | 6 | 15 | 5 | 5 | 1 | 1 | 3 | 8 | 8 | 10 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
Go/No-Go Probability | 95.26% | 100% | 93.68% | 96.84% | 98.42% | 85.79% | 100% | 85.79% | 100% | 95.26% | 92.11% | 96.84% | 82.63% | 100% | 96.84% | 85.79% | 92.11% | 96.84% | 93.68% | 92.11% | 92.11% | 77.89% | 93.68% | 93.68% | 100% | 100% | 96.84% | 88.95% | 88.95% | 85.79% | 96.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 95.26% | 95.26% | 89.25% | 86.43% | 85.06% | 72.98% | 72.98% | 62.61% | 62.61% | 59.64% | 54.93% | 53.2% | 43.96% | 43.96% | 42.57% | 36.52% | 33.64% | 32.57% | 30.52% | 28.11% | 25.89% | 20.17% | 18.89% | 17.7% | 17.7% | 17.7% | 17.14% | 15.25% | 13.56% | 11.63% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27% | 11.27%
Expected Cash Flow | 0 | 0 | 0 | -446.2327 | -172.8565 | -850.6357 | -547.3169 | 0 | 0 | -1721.6478 | -2087.3949 | -549.3145 | -1063.9354 | -6593.5995 | 0 | -4256.9204 | -1825.9948 | -1345.4698 | -8143.6333 | -1525.8597 | -7448.6046 | 0 | 0 | 0 | -176.9923 | -176.9923 | -6902.7004 | 0 | 0 | 0 | -15123.8444 | -337990.3679 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461 | 19434.4461
Expected IRR | 2025-01-01: 1.808%
Projects Reaching NTP | 2025-01-01: 11.27%
DevEx Costs | 2025-01-01: -273200
Formulas:
Start Date = EDATE([Start Date, row below], [Duration (months), row below])

## IX cost
|  | Project size (MW) | Extension cost for 0.1mi | Distance to POI (mi) |  |  |  | Fixed
|  | 3 | 30000 | 1.5 |  |  | F | 250000
[7 empty] | V | 65000
| Cost Component | No Extension(0 mi) | 0.1 mi Extension | 0.5 mi Extension | 1.0 mi Extension | Distance Sensitivities
~Base | Utility Fees & Minor Upgrades (Studies, tap hardware) | 75000 | 75000 | 75000 | 75000 | 75000
| Project-Owned Interconnection (transformers, switchgear, recloser, metering, labor) | 445000 | 445000 | 445000 | 445000 | 445000
| Subtotal | 520000 | 520000 | 520000 | 520000 | 520000
~POI Variable | Line Extension(3-phase overhead, poles, conductor, labor) | 0 | 30000 | 150000 | 300000 | 450000
| Total Interconnection | 520000 | 550000 | 670000 | 820000 | 970000
Assumptions | no specific interconnection standards to apply (NYISO)
assuming 12 kv line
ix study/application (CESIR), plus standard tap fees for one new pole and minor feeder hardware
maxing at 5mw to not trigger
$1 mil/ mile

## Old Simplified Financial Model
Risk Category | DevEx Scenario | CapEx Scenario | DevEx | Increase in CapEx | Approval Risk Rating | Go/No-Go Probability |  |  |  |  | Cost Low Bound | Cost Upper Bound | CapEx Low Bound | CapEx Upper Bound
Site Control | Best |  | 7700 | 0 | 5 | 0.85714 |  |  |  |  | 7700 | 9000 | 0 | 0
Permitting | Best |  | 40000 | 0 | 6 | 0.82143 |  |  |  |  | 40000 | 90000 | 0 | 0
Interconnection | Best | Best | 146250 | 250000 | 8 | 0.75 |  |  |  |  | 146250 | 157750 | 250000 | 2000000
Design | Best | Best | 44500 | 150000 | 2 | 0.96429 |  |  |  |  | 44500 | 52500 | 150000 | 2000000
Environmental | Best | Best | 26750 | 0 | 6 | 0.82143 |  |  |  |  | 26750 | 53000 | 0 | 250000
Total Dev Spend | 265200
Total Additional CapEx Spend | 400000
Base Case CapEx Spend | 3000000
Total CapEx Spend | 3400000
OpEx | 37500
Revenue | 220000
ITC | 1020000
Simple Financial Model
Base Case | Year Since Development Start
| 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Phase | Development | NTP and Construction | COD
DevEx | 265200
CapEx |  | 3400000
OpEx |  |  | 37500 | 37875 | 38253.75 | 38636.2875 | 39022.6504 | 39412.8769 | 39807.0056 | 40205.0757 | 40607.1265 | 41013.1977 | 41423.3297 | 41837.563 | 42255.9386 | 42678.498 | 43105.283 | 43536.3358 | 43971.6992 | 44411.4162 | 44855.5303 | 45304.0856 | 45757.1265 | 46214.6978 | 46676.8447 | 47143.6132 | 47615.0493 | 48091.1998 | 48572.1118 | 49057.8329 | 49548.4113 | 50043.8954
Benefits |  |  | 1020000
Revenue |  |  | 220000 | 222200 | 224422 | 226666.22 | 228932.8822 | 231222.211 | 233534.4331 | 235869.7775 | 238228.4752 | 240610.76 | 243016.8676 | 245447.0363 | 247901.5066 | 250380.5217 | 252884.3269 | 255413.1702 | 257967.3019 | 260546.9749 | 263152.4447 | 265783.9691 | 268441.8088 | 271126.2269 | 273837.4891 | 276575.864 | 279341.6227 | 282135.0389 | 284956.3893 | 287805.9532 | 290684.0127 | 293590.8528
Cash Flow | -265200 | -3400000 | 1202500 | 184325 | 186168.25 | 188029.9325 | 189910.2318 | 191809.3341 | 193727.4275 | 195664.7018 | 197621.3488 | 199597.5623 | 201593.5379 | 203609.4733 | 205645.568 | 207702.0237 | 209779.0439 | 211876.8344 | 213995.6027 | 216135.5587 | 218296.9143 | 220479.8835 | 222684.6823 | 224911.5291 | 227160.6444 | 229432.2508 | 231726.5734 | 234043.8391 | 236384.2775 | 238748.1203 | 241135.6015 | 243546.9575
Go/No-Go Probability | 41.83% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Cumulative Success Probability (up until current period) | 100% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83% | 41.83%
Expected Cash Flow | -265200 | -1422128.15 | 502973.2647 | 77098.168 | 77869.1497 | 78647.8412 | 79434.3196 | 80228.6628 | 81030.9494 | 81841.2589 | 82659.6715 | 83486.2682 | 84321.1309 | 85164.3422 | 86015.9856 | 86876.1455 | 87744.9069 | 88622.356 | 89508.5796 | 90403.6654 | 91307.702 | 92220.779 | 93142.9868 | 94074.4167 | 95015.1609 | 95965.3125 | 96924.9656 | 97894.2152 | 98873.1574 | 99861.889 | 100860.5079 | 101869.1129
Expected IRR (for portfolio of projects) | 5.116%
Projects Reaching NTP | 41.83%
IRR of successful projects | 6.103%

## ArcadiaProjectModel
Risk Category | Responsible Party | Counterparty | Type | PrimaryTask | Required | SubTask | Description | Proof Point | Blocking | Budget | Min Time (days) | Median Time (days) | Max Time (days) | Risk | Type of Spend | Status | Completion Time Range Start | Completion Time Range End | Blocked by
Permitting | Developer | Code Enforcement Officer | Relationship Building | Due Diligence | TRUE | Initial AHJ Consultation | Initial consultation with AHJ to confirm understanding of ordinance + permitting process | Record of email exchange and phone call | Initial Concept Design, Pre-Application Meeting | 0 |  | 7 |  | 2 | Labor
Permitting | Developer |  | Research | Due Diligence | TRUE | Initial Concept Design | High level layout of project with current understanding of site restrictions (all desktop) |  | Geotechnical Analysis, Boundary & Topographic Property Survey, Preliminary Wetlands Assessment, Wetland Delineation Report, Ecological Assessment, Environmental Site Assessment (ESA) Phase I, Pre-Application Meeting | 0 |  | 14 |  | 2 | Labor
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | FALSE | Preliminary Wetlands Assessment | Perform a site visit to confirm presence or absence of freshwater wetlands on project site, map out limits if observed |  |  | 2750 |  | 28 |  | 2
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | FALSE | Wetland Delineation Report | Requires a site visit, review of federal, state, and local documents, and identification of any wetlands and their flood hazard potential. |  | Environmental Site Assessment (ESA) Phase I, Ecological Assessment | 12500 |  | 56 |  | 4 |  |  | March | November |  | if near wetland, want to skip preliminary and do full report earlier or just do preliinary to see if full report is needed
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | TRUE | Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies. |  | Special Use Application Submission, USFWS Concurrence, NYNHP Concurrence | 12500 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | FALSE | Environmental Site Assessment (ESA) Phase I |  |  | Special Use Application Submission, Site Plan Design | 7500 |  | 56 |  | 4
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | TRUE | Boundary & Topographic Property Survey | A full Boundary Survey of the perimeter of the parcel whichshall include any necessary deed and plan research |  | Title Report, PILOT Agreement, Site Plan Design | 13500 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | FALSE | Geotechnical Analysis | Conduct field borings and testing to ensure subsurface can support solar farm |  | Construction Plan, Site Plan Design | 26500 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Due Diligence | FALSE | Cultural Resource Survey | Assessment of potential impacts of a project on historic/cultural properties or archaeological resources |  | SHPO Concurrence | 20000 |  | 28 |  | 1
Permitting | Developer | Town Residents | Relationship Building | Site Plan Application Package | TRUE | Notify and obtain consent from abutters | Get signatures from all nearby property owners consenting to building the solar system |  | Site Plan Application Submission | 0 |  | 28 |  | 4
Permitting | Developer | Code Enforcement Officer | Relationship Building | Special Use Permit Application Package | TRUE | Pre-Application Meeting | Pre-application meeting with the code enforcement officer to obtain recommended procedures, and technical assistance for the permitting process. Meet with other local stakeholders |  | Notify and obtain consent from abutters, Site Plan Design, Property Operation and Maintenance Plan, Glare Study, Noise Study, Landscaping Plan, Construction Plan, PILOT Agreement, Decomissioning Agreement, Visual Resource Assessment | 0 |  | 84 |  | 2
Permitting | Developer |  | Submission/Coordination | Special Use Permit Application Package | TRUE | Property Operation and Maintenance Plan | Describes maintenance and property upkeep |  | Special Use Application Submission | 0 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Special Use Permit Application Package | TRUE | Glare Study | Assessment of potential glint and glare effects from solar photovoltaic systems |  | Special Use Application Submission | 1000 |  | 84 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Special Use Permit Application Package | TRUE | Noise Study | Identify current & anticipated noise levels + mitigation measures |  | Special Use Application Submission | 1000 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Site Plan Application Package | TRUE | Landscaping Plan | Includes landscaping design to accomodate ordinance, such as screening or native vegetation requirements |  | Site Plan Application Submission | 0 |  | 28 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Special Use Permit Application Package | TRUE | Construction Plan | Outline of construction activities to occur and timeline |  | Special Use Application Submission | 0 |  | 28 |  | 1
Permitting | Developer | County IDA | Submission/Coordination | Special Use Permit Application Package | TRUE | PILOT Agreement | Enter into PILOT agreement with county Industrial Development Agency |  | Special Use Application Submission | 0 |  | 84 |  | 3
Permitting | Developer | Planning Board | Submission/Coordination | Special Use Permit Application Package | TRUE | Decommissioning plan | Ensures site will be restored to pre-dev condition | Signed plan | Decomissioning Agreement | 0 | 7 | 15 | 30 | 1
Permitting | Developer | Planning Board, Landowner | Submission/Coordination | Special Use Permit Application Package | TRUE | Decommissioning Agreement | Agree on LO & applicant obligations, and pay financial security of 150% of est. removal cost | Record of agreement (at office of Wayne County Clerk) | Special Use Application Submission | 180000 |  | 5 |  |  | Bond
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Special Use Permit Application Package | TRUE | Visual Resource Assessment | Provide an analysis of visual impact from public roads, parks, adjacent residential structures, and historic properties. |  | Special Use Application Submission | 12950 |  | 84 |  | 1
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Site Plan Application Package | TRUE | Stormwater Management Plan | Submit a stormwater management plan approved by the Department of Environmental Quality to ensure runoff and erosion is safe |  | Site Plan Application Submission | 1250 |  | 56 |  | 1
Permitting | Civil Engineer/Consultant | NYS DEC (Department of Environmental Conservation) | Submission/Coordination | Special Use Permit Application Package | TRUE | SEQR Environmental Assessment Form (EAF) Part I | State-mandated environmental review, requires Full Environmental Assessment Form (FEAF) submission |  | Special Use Application Submission | 0 |  | 28 |  | 3
Permitting | Developer | Town Residents | Relationship Building | Special Use Application Coordination | FALSE | Community Engagement Meeting | Hold a public meeting before the Planning Commission's public hearing. Notify the zoning administrator and adjacent property owners in writing and advertise the meeting in a newspaper of record. |  | Public Hearing | 0 |  | 28 |  | 5
Permitting | Civil Engineer/Consultant | Developer | Report/Study | Site Plan Application Package | TRUE | Site Plan Design | Ensure site design complies with restrictions as laid out in site plan application / solar odinance (includes emergency requirements, official licensing, contact information, three line diagram, etc) |  | Site Plan Application Submission, Community Engagement Meeting | 45000 |  | 84 |  | 1
Permitting | Developer | Planning Board | Submission/Coordination | Site Plan Application Coordination | TRUE | Site Plan Application Submission | Includes info about property lines, contact info, electrical diagrams, etc |  | Special Use Application Submission, Site Plan Application Review | 0 |  | 7 |  | 1
Permitting | Planning Board | Developer | Submission/Coordination | Site Plan Application Coordination | TRUE | Site Plan Application Review | Review of site plan by town planning board |  | Special Use Application Submission | 0 |  | 84 |  | 10
Permitting | Developer | Town Board | Submission/Coordination | Special Use Application Coordination | TRUE | Special Use Application Submission | Submit special / conditional use permit to planning and zoning office |  | CESIR Study Review, Public Hearing, Community Engagement Meeting | 35000 |  | 28 |  | 1
Permitting | Developer | Town Board | Relationship Building | Special Use Application Coordination | TRUE | Public Hearing | A public hearing will be held, allowing parties in interest and citizens to be heard. Notice of the hearing will be published in a newspaper with general circulation in the county. |  | Town Board Review | 12000 | 62 | 84 |  | 1
Permitting | Town Board | Developer | Submission/Coordination | Special Use Application Coordination | TRUE | Town Board Review | The Planning Commission reviews the application and provides a report to the Board of Supervisors. If the Planning Commission does not act within 100 days, the application is considered approved. |  | Final Special Use Permit Approval | 0 |  | 84 |  | 10
Permitting | Town Board | Developer | Submission/Coordination | Special Use Application Coordination | TRUE | Final Special Use Permit Approval | The Board of Supervisors reviews the Planning Commission's recommendation and votes on the application during a scheduled meeting. They may place conditions on the permit if approved. |  |  | 0 |  | 84 |  | 10
Permitting | Civil Engineer/Consultant | SHPO (NYS State Office of Historic Preservation) | Submission/Coordination |  | FALSE | SHPO Concurrence |  |  |  | 400 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | NYS Department of Agriculture | Submission/Coordination |  | TRUE | Agriculture District Concurrence |  |  |  | 400 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | NYS Department of Agriculture | Report/Study |  | FALSE | Agricultural Market Law: Notice of Intent | Determines whether you have to pay a nominal amount in increased property taxes |  |  | 400 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | Federal Agency | Submission/Coordination |  | TRUE | FAA Determination |  |  |  | 400 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | Federal Agency | Submission/Coordination |  | FALSE | USFWS Concurrence | Obtain negative determination letter confirming habitat suitability for protected species |  |  | 400 |  | 7 |  | 1
Permitting | Civil Engineer/Consultant | NYNHP (National Heritage Program_ | Submission/Coordination |  | FALSE | NYNHP Concurrence | Obtain negative determination letter confirming habitat suitability for protected species |  |  | 400 |  | 0 |  | 1
Interconnection |  | Utility | Relationship Building |  |  | Preapplication (Informal Request) | Request electric system information |  | Preapplication (Formal Request) | 0 |  | 7 |  | 2
Interconnection |  | Utility | Submission/Coordination |  |  | Preapplication (Formal Request) | Nonrefundable fee for preapplication report |  | Site Plan – Utility Interconnection Plan | 750 |  | 7 |  | 2
Interconnection |  | Utility | Report/Study |  |  | Site Plan – Utility Interconnection Plan | Diagram and documentation showing how the system connects to the electrical grid |  | Standard Interconnection Application | 0 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination |  |  | Standard Interconnection Application | Submit filled-out application form |  | Preliminary Review | 750 |  | 28 |  | 1
Interconnection |  | Utility | Relationship Building |  |  | Preliminary Review | Discuss interconnection request and preliminary interdependency determination. |  | CESIR Study Application | 0 |  | 28 |  | 3
Interconnection |  | Utility | Submission/Coordination |  |  | CESIR Study Application | Confirm that you want to proceed with CESIR study and submit requisite information |  | CESIR Deposit Payment |  |  | 7 |  | 2 |  |  |  |  | Site plan
Interconnection |  | Utility | Report/Study |  |  | CESIR Deposit Payment |  |  | CESIR Study | 45000 |  | 7 |  | 1
Interconnection | Utility | Developer | Report/Study |  |  | CESIR Study | Utility does the study |  | CESIR Study Review |  |  | 56 |  | 10
Interconnection |  | Utility | Submission/Coordination |  |  | CESIR Study Review | Review cost determinations |  | NY Standardized Interconnection Contract | 0 |  | 168 |  | 10
Interconnection |  | Utility | Submission/Coordination |  |  | NY Standardized Interconnection Contract | Come to terms on exact costs of upgrade + 25% payment of total cost quoted |  | Construction Planning Meeting, Interconnection Costs Paid | 1000000 |  | 28 |  | 5
Interconnection |  | Utility | Relationship Building |  |  | Construction Planning Meeting | Identify tasks and milestones for construction |  |  | 0 |  | 28 |  | 1
Interconnection |  | Utility | Submission/Coordination |  |  | Interconnection Costs Paid | Remaining balance of IX cost paid |  |  | 0 |  | 28 |  | 1
Site Control |  | Property Owner |  |  |  | Letter of Intent | Sign LOI with landowner |  | Preliminary Title Search, Standard Interconnection Application |  |  | 30 |  | 4
Site Control |  | Property Owner |  |  |  | Preliminary Title Search | Preliminary title search for encumbrances, deed's of trusts, and other potential title issues |  | Execute Lease Agreement, Title Policy Report |  |  | 50 |  | 4 |  | #REF!
Site Control |  | Property Owner |  |  |  | Execute Lease Agreement | Negotiate and execute lease agreement with landlord |  | Record Lease Memorandum |  |  | 60 |  | 10 |  | #REF!
Site Control |  | Property Owner |  |  |  | Record Lease Memorandum | A Memorandum of Lease is a recordable document that provides public notice of a lease's existence |  |  |  |  | 15 |  | 1 |  | #REF!
Site Control |  | Property Owner | Report/Study |  |  | Title Policy Report | Title policy and report containing essential information about the property's title, including any recorded claims, encumbrances, and other matters |  | Lease Area and Easement Plan | 250 |  | 7 |  | 1 |  | #REF!
Site Control |  | Property Owner | Report/Study |  |  | Lease Area and Easement Plan | Prepare a Lease Area Plan showing the area access and utility easements required, certified by a professional surveyor |  | Special Use Application Submission | 3500 |  | 0 |  | 1 |  | #REF!
Site Control |  | Property Owner | [9 empty] | 0
Site Control |  | Property Owner | [9 empty] | 0
Site Control |  | Property Owner | [9 empty] | 0
Site Control |  | Property Owner | [9 empty] | 0
Offtake / Incentives | Charles | [10 empty] | 0
Procurement | Elias | [10 empty] | 0

## PermittingInputs
Requirement ID | Requirement | Description | Type of Work | Required | AHJ | Min Time | Median Time | Max Time | Time Length | Duration Variability | Labor Time | Labor Costs | Application fee | Fixed Deadline | Pre-Requirements | Professional Engineer/Consultant Needed? | Automatable | Source
1 | Special Use Permit Application Form | Official application form submitted to the Town Planning Board | Application Form | Yes | Township | 30 | 90 | 120 | <4 months | Fixed/variable | 30 hours | 5000 | $200-600 |  | Environmental Assessment Form, Site Plan |  |  | https://www.cityofrochester.gov/sites/default/files/migrated/WorkArea-DownloadAsset.aspx-id-21474848659.pdf | GZA and Colliers
2 | Environmental Assessment Form | document used under the State Environmental Quality Review Act (SEQRA) to help state or local agencies evaluate the potential environmental impacts of a proposed project before making a decision. | Application Form | Yes | State |  |  |  |  | Variable | 1 | 1500 |  |  |  |  | Yes | https://dec.ny.gov/regulatory/permits-licenses/seqr/eaf-workbooks | https://dec.ny.gov/sites/default/files/2024-08/feafpart1.pdf
3 | Site Plan Application Form |  | Application Form |  | Township |  |  |  |  | Variable | 30 hours | 5000
4 | Signed Lease Agreement | A signed lease agreement with the landowner is required for a special use permit application | Documentation | Yes | Township | 90 | 120 | 180 | 3-6 months | Variable |  |  |  |  | Landowner engagement
5 | Geotechnical Study/Report | Assessment of soil conditions, groundwater impact, and subsurface geology. | Study | Yes | Township |  | 90 |  | 3 months | Variable |  | 16000-26000 |  |  | Landowner engagement | Yes | No | Tony
6 | Certified Public Notification Proof | Proof of notification sent to landowners within 200 feet (certified mail receipts) | Documentation | Yes | Township
| Site Plan – Property Boundaries & Topological Features | Must include a map showing roads, existing structures, water bodies, and adjacent properties | Study | Yes | Township |  | 90 |  | 2 months | Variable |  | 13500 |  |  |  | Yes | Maybe
| Site Plan – Solar Array Layout | Diagram showing the placement of panels, inverters, and other key equipment | Study | Yes | Township |  | 120 |  | 4 months | Variable |  | 45000 |  |  | Geotechnical study | Yes
| Site Plan – Grading & Excavation Plan | Document showing elevation changes, cut/fill areas, and soil disturbance | Study | Yes | Township |  | 120 |  | 4 months | Variable | [5 empty] | Yes
| Site Plan – Stormwater & Erosion Control Plan | Compliance with NYS DEC guidelines for managing runoff and preventing soil erosion | Study | Yes | Township |  | 120 |  | 4 months | Variable | [5 empty] | Yes
| Site Plan – Vegetation Plan | Clearing and replanting details, including preservation of existing trees and new plantings | Study | If required (more than 3 trees need to be cut) | Township |  | 120 |  | 4 months | Variable | [5 empty] | Yes
| Site Plan – Utility Interconnection Plan | Diagram and documentation showing how the system connects to the electrical grid | Study | Yes | Township |  | 120 |  | 4 months | Variable | [5 empty] | Yes
| Site Plan -- Stormwater Pollution Prevention Plan | A Stormwater Pollution Prevention Plan (SWPPP) is a site-specific, written document developed to identify potential sources of stormwater pollution at a construction site or industrial facility | Study | Yes | Township |  | 120 |  | 4 months | Variable | [5 empty] | Yes
| Preliminary Wetlands Assessment | Site visit to confirm the presence or absence of wetlands on the site. | Study | Yes |  |  | 15 |  | <1 month | Variable |  | 2750 | [5 empty] | GZA and Colliers
| Wetlands, Aquifer, Wildlife Protection Study | Identifies protected zones and contamination risks | Study | If required |  |  | 90 |  | 3 months | Variable |  | 7800-9300 | [5 empty] | Colliers, GZA
| State Pollutant Discharge Elimination System (SPDES) Notice of Intent | It comes with supporting documents such as a Stormwater Pollution Prevention Plan (SWPPP) and a Soil Erosion & Sediment Control Plan, which show how the project will manage stormwater and minimize erosion during construction. | Application Form | Yes | State |  | 15 |  | <1 month | Variable |  | 500 |  |  | Stormwater & Erosion Control Plan
| Decommissioning Plan | Plan detailing how the site will be restored and equipment removed at end of project life. Can include restoration of soil areas, vegetation depending on the county. | Study | Yes | Township |  | 15 |  | <1 month | Variable | 10-20 hours | 1500-3000 | [5 empty] | http://www.townofcanandaigua.org/documents/files/County%20Road%2010%202890%202021-07-07%20DEcommissioning%20Plan.pdf
| Decommissioning Agreement | Requires agreement between landowners, project developers, system operators | Documentation | Yes | Townshipp | 30 | 60 | 90 | 1-3 months | Fixed | 5-10 hours | 750-1500 |  |  | Financial Security
| Decommissioning Financial Security (Bond/Escrow) | 110-150% of removal cost posted in a financial security account, or through a letter of credit. | Documentation | Yes | Township
| Road Use Agreement/permit | Developer must repair town roads damaged by construction traffic; includes financial bond. | Documentation | Some AHJ | Township |  |  |  |  | Fixed | 12 hours | 2000
| Traffic Impact Study | Assesses impact on local roads, school bus routes, and emergency access. | Study | If required | Township |  |  |  |  | Variable | 20-30 hours | 2600-3900 | [5 empty] | https://documents.dps.ny.gov/public/Common/ViewDoc.aspx?DocRefId=802c328d-0000-cd40-99d4-058f4d5c931d
| Viewshed & Line-of-Sight Analysis (Visual Impact Assessment) | At a minimum, a line-of-sight profile analysis shall be provided. Depending upon the scope and potential significance of the visual impacts, additional impact analyses, including, for example, a digital viewshed report, may be required to be submitted by the applicant. | Study | If required (project is bigger than 10 acres) | Township |  | 120 |  | 4 months | Variable |  | 5000-20000 | [5 empty] | https://www.eagleeyedesign.co.uk/how-much-does-an-lvia-cost#:~:text=Project%20Size%20and%20Complexity,numerous%20viewpoints%2C%20&%20advanced%20visualisations.
| Screening and Landscaping Plan | to show adequate measures to screen through landscaping, grading, or other means so that views of Solar Panels and Solar Energy Equipment shall be minimized as reasonably practical from public roadways and adjacent properties to the extent feasible. | Study | If required (project is bigger than 10 acres) | Township |  | 30 |  | 1 month | Variable | 8 hours | 1000 |  |  |  |  | Maybe
| Noise Study | Evaluation of noise levels from inverters, transformers, and construction activities. | Study | Some AHJ | Township |  | 30 |  | 1 month | Variable | 11 hours | 1540 |  |  |  |  | No
| Glare & Reflection Study | Ensures no hazardous glare for roads, aircraft, or nearby properties. | Study | Some AHJ | Township |  | 30 |  | 1 month | Variable | 8 hours | 1120 |  |  |  |  | Maybe
| Operations & Maintenance Plan | Document outlining long-term system maintenance, vegetation control, and repairs | Study | Yes | Township |  | 15 |  | < 1 month | Variable | 4 hours | 480 | [5 empty] | https://mccmeetingspublic.blob.core.usgovcloudapi.net/lansingny-meet-8e9e613ac40e4bef831cdee66b724566/ITEM-Attachment-001-636b7f97cf2a4191ab35c9bfdfbd2f1a.pdf#:~:text=3,once%20per%20month%2C%20or%20as
| Phase I Environmental Site Assessment (SEQRA Review) | Based on the environmental assessment form, a committee will decide whether this is required. If required, must include a report on ecological impact and mitigation strategies. 4500 for labor costs, 1000 for travel, equipment, etc | Study | If required | SEQRA |  | 15 |  | < 1 month | Variable |  | 4000-5500
| Native Vegetation Plan | Must implement, and maintain native vegetation to the extent practicable pursuant to a vegetation management plan by providing native perennial vegetation and foraging habitat beneficial to game birds, songbirds, and pollinators. | Study | If required (on agricultural land)
| Coordinated Electric System Interconnection Review (CESIR) |  |  | Yes | Township
| Community Engagement Report | Documentation of outreach efforts, meetings, and community feedback. | Documentation | Some AHJ | Township
| Complaint Resolution Plan | Plan for handling community complaints related to construction and operation. |  | Some AHJ
| FAA Determination of No Hazard (DNH) | Federal Aviation Administration confirmation that the project does not pose hazards to air traffic. | Documentation | Some AHJ | Federal |  |  |  |  | Fixed | 4 | 500 |  |  |  |  | Maybe | GZA, Environmental permitting
| Structural Archeological Assessment Form | Inventory of historical and culturally significant structures in the project area. Obtain written confirmation of determination from the NYS State Office of Historic Preservation; |  | Some AHJ |  |  |  |  | 6-8 weeks | Fixed | 10 | 1000 | [5 empty] | https://www.nysl.nysed.gov/libdev/construc/shpo.htm | https://extapps.dec.ny.gov/docs/permits_ej_operations_pdf/shpaapplguide.pdf | https://extapps.dec.ny.gov/docs/permits_ej_operations_pdf/saaf.pdf
| Stage 1 Archaeology Survey | Study determining if the project site contains any significant archaeological artifacts, both through literature research and fieldwork |  | If required
| Emergency Response Plan | Site emergency protocols for fire, medical, and disaster response. |  | Some AHJ
| Construction Plan |  |  | Some AHJ
| Agricultural Impact Statement | Statement to determine the impact of the project on agriculture in the township. | Documentation | If required (project > 5MW) and only in some AHJ | [6 empty] | 2025-04-08 | 500
| Insurance & Liability Proof | Proof of liability insurance coverage | Documentation | Some AHJ | [5 empty] | Fixed | [7 empty] | https://locallaws.dos.ny.gov/sites/default/files/drop_laws_here/ECMMDIS_appid_DOS20230109123423/Content/090213438031d8f1.pdf#:~:text=i,A
| Community Benefit Agreement | Developer may be required to provide payments or public improvements to offset project impacts. A common type of community benefit is often the PILOT program | Documentation | Some AHJ
| Payment in Lieu of Taxes (PILOT) Agreement | Negotiation with the town for tax payments in place of standard property taxes. | Documentation | Some AHJ |  |  |  |  | 2-4 months | Fixed |  |  | TBD
| Building Permit | Ensures project meets NYS Building Code; must be approved before work begins. | Application Form | Yes | State |  |  |  |  | Fixed |  | 500 | $200 / 1000 sq ft |  |  | Yes | Maybe | https://dos.ny.gov/system/files/documents/2023/07/0301-f.pdf | https://dos.ny.gov/system/files/documents/2022/12/dos-admin-and-enforcement-fee-schedule-2022-08.pdf
| Electrical Permit | Ensures project meets National Electric Code (NEC) for safe electrical interconnection. | Application Form | Yes | State |  |  |  |  | Fixed |  | 500
| Public Hearings |  | Meeting | Yes | Township |  |  |  | 4 months | Fixed | 40 | 10000
| Total Estimated Costs Best Case (Lower Estimate) | 109140
| Total Estimated Costs Best Case (Upper Estimate) | 120390
| Total Estimated Costs Worst Case (Lower Estimate) | 130040
| Total Estimated Costs Worst Case (Upper Estimate) | 140590
109140
130040
140590
Design Requirements
| Security & Fencing Plan | Plan for a 7-ft security fence with self-locking gate per zoning requirements
| Equipment Specifications | Ensure compliance with zoning, electrical, and building codes. |  | Yes
| Glare Mitigation Statement | Report proving panels have anti-reflective coatings and will not cause hazardous glare
| Lighting Plan | Documentation of shielded, downcast lighting design to prevent light pollution
rare
| Drain Tile Assessment | Evaluation of subsurface drainage systems and potential impacts on agricultural land.
| Unanticipated Discovery Plan | Plan for managing unexpected archaeological finds during construction.
| EMF Exposure Study | Confirms EMF levels ≤ 2 milligauss at boundaries
| Soil Analysis & Pre-Development Conditions | Required if the site is on Prime Farmland; pre- and post-construction soil sampling required. Part of geotechnical study typically?
Townships Covered
Town of Springwater
Arcadia
| Meredith | [16 empty] | https://locallaws.dos.ny.gov/sites/default/files/drop_laws_here/ECMMDIS_appid_DOS20230109123423/Content/090213438031d8f1.pdf#:~:text=i,A

## NY Permitting Database
Requirement | Description | Description II | Permit Category | Typical Length | Professional Certification
Special Use Permit Application Form | official application form submitted to the town planning board
Certified Public Notification Proof | proof of notification sent to landowners within 200 feet (certified mail receipts)
Site Plan – Property Boundaries & Features | must include a map showing roads, existing structures, water bodies, and adjacent properties
Site Plan – Solar Array Layout | diagram showing the placement of panels, inverters, and other key equipment
Site Plan – Grading & Excavation Plan | document showing elevation changes, cut/fill areas, and soil disturbance
Site Plan – Stormwater & Erosion Control Plan | compliance with nys dec guidelines for managing runoff and preventing soil erosion
Site Plan – Vegetation Plan | clearing and replanting details, including preservation of existing trees and new plantings
Site Plan – Utility Interconnection Plan | diagram and documentation showing how the system connects to the electrical grid
Glare Mitigation Statement | report proving panels have anti-reflective coatings and will not cause hazardous glare
Lighting Plan | documentation of shielded, downcast lighting design to prevent light pollution
Security & Fencing Plan | plan for a 7-ft security fence with self-locking gate per zoning requirements
Visual Impact Assessment | if the project is over 10 acres, must include viewshed analysis and landscaping plan
Landscaping Plan
Environmental Impact Assessment (SEQRA Review) | if required, must include a report on ecological impact and mitigation strategies
Prime Farmland Impact Study | report detailing if the project affects prime farmland; if so, must prove <50% land usage
Pollinator-Friendly Vegetation Plan | must document 20% of the project planted with native species
Decommissioning Plan | plan detailing how the site will be restored and equipment removed at end of project life
Decommissioning Financial Security (Bond/Escrow) | 125% of removal cost posted in a financial security account
Operations & Maintenance Plan | document outlining long-term system maintenance, vegetation control, and repairs
Equipment Specifications | ensure compliance with zoning, electrical, and building codes.
Road Use Maintenance Agreement (RUMA) | agreement detailing road use, maintenance responsibilities, and repairs due to construction traffic.
Socioeconomic Report | assessment of project benefits, including tax revenue, job creation, and local economic impact.
Community Engagement Report | documentation of outreach efforts, meetings, and community feedback.
Complaint Resolution Plan | plan for handling community complaints related to construction and operation.
FAA Determination of No Hazard (DNH) | federal aviation administration confirmation that the project does not pose hazards to air traffic.
Route Evaluation & Traffic Study | analysis of transportation impacts, road conditions, and mitigation measures.
Noise Study | evaluation of noise levels from inverters, transformers, and construction activities.
Geology & Hydrology Report | assessment of soil conditions, groundwater impact, and subsurface geology.
Wetland Delineation Report | identification and mapping of wetlands on or near the project site.
Ecological Assessment | evaluation of habitat and wildlife impacts, including mitigation strategies.
HDD Inadvertent Return Contingency Plan | plan to prevent and manage drilling fluid spills from horizontal directional drilling.
SHPO Concurrence | state historic preservation office approval regarding historical site impacts.
Historic Resource Survey | inventory of historical and culturally significant structures in the project area.
Phase 1 Archaeology Survey | study determining if the project site contains any significant archaeological artifacts.
Visual Resource Assessment | analysis of project visibility and aesthetic impacts from public viewpoints.
Landscape Plan | aesthetic integration and screening using vegetation and natural barriers.
Emergency Response Plan | site emergency protocols for fire, medical, and disaster response.
Drain Tile Assessment | evaluation of subsurface drainage systems and potential impacts on agricultural land.
Unanticipated Discovery Plan | plan for managing unexpected archaeological finds during construction.
EMF Exposure Study | evaluates electromagnetic field safety | Confirms EMF levels ≤ 2 milligauss at boundaries | Construction Permit
Fire Safety & Emergency Plan | ensures safe response to incidents | Requires first responder coordination and training | Construction Permit
Interconnection Agreement | confirms grid compatibility | Agreement with LIPA or local utility provider | Construction Permit
Insurance & Liability Report | provides financial risk protection | Proof of liability insurance coverage | Construction Permit
Environmental Impact Study (EIS) | assesses overall environmental effects | SEQRA compliance, impact on land, water, air, traffic, and wildlife | Special Exception Approval
Wildlife & Habitat Study | protects wildlife corridors and endangered species | Survey of affected species and mitigation strategies | Special Exception Approval
Stormwater Management Plan | prevents runoff and erosion | SWPPP compliance, drainage system design | Special Exception Approval & Construction Permit
Wetlands & Aquifer Protection Study | ensures groundwater and wetland protection | Identifies protected zones and contamination risks | Special Exception Approval
Clearing Calculations Survey | determines land clearing impact | Required for parcels over 10 acres | Special Exception Approval
Traffic Impact Study | evaluates construction and operational traffic | Identifies needed road improvements | Special Exception Approval
Substation & Infrastructure Plan | determines grid compatibility and required upgrades | Assesses new poles, transformers, or substations | Special Exception Approval & Utility Interconnection
Decommissioning Plan & Bond | ensures proper removal of system at project’s end | Includes cost estimate and financial bond | Special Exception Approval & Decommissioning Compliance
Glare & Reflection Study | prevents hazardous solar glare | Assesses potential reflection impact | Special Exception Approval
Noise Compliance Study | ensures compliance with noise ordinances | Measures inverter and transformer noise levels | Conditionally Required for Special Exception; Always Required for Construction Permit & Post-Construction Compliance
Site Plan Approval | zoning & planning | Layout, components, access, setbacks, landscaping, stormwater plans. | Special Use Permit
Special Use Permit Application | land use & zoning | Required for all commercial-scale projects; includes environmental and zoning compliance studies. | Special Use Permit
Environmental Impact Study (EIS) | seqra compliance | Analyzes environmental effects, including wetlands, habitat, noise, stormwater, and land use impacts. | Special Use Permit
Wildlife & Habitat Study | environmental compliance | Evaluates potential disruptions to local wildlife corridors and habitats. | Special Use Permit
Stormwater & Erosion Control Plan | environmental protection | Ensures proper drainage and erosion control measures are in place. | Special Use Permit & Construction Permit
Wetlands & Aquifer Protection Study | water resource protection | Required if the project site is near protected wetlands or groundwater resources. | Special Use Permit
Clearing & Grading Plan | land use compliance | Ensures compliance with land alteration rules, including tree removal and grading. | Special Use Permit & Construction Permit
Traffic Impact Study | road use & public safety | Assesses impact on local roads, school bus routes, and emergency access. | Special Use Permit
Road Use Agreement | infrastructure protection | Developer must repair town roads damaged by construction traffic; includes financial bond. | Special Use Permit & Pre-Construction Compliance
Substation & Infrastructure Plan | utility compliance | Required if grid interconnection necessitates upgrades (e.g., new substations, transmission lines). | Special Use Permit & Utility Interconnection
Noise Study | community & public health | Evaluates anticipated noise levels from inverters, transformers, and construction activity. | Special Use Permit (conditionally required) & Construction Permit
Glare & Reflection Study | traffic & aviation safety | Ensures no hazardous glare for roads, aircraft, or nearby properties. | Special Use Permit
Viewshed & Line-of-Sight Analysis | aesthetic & visual impact | Provides scaled visual renderings of the solar project at installation, 5 years, and 10 years. | Special Use Permit
Soil Analysis & Pre-Development Conditions | agricultural land protection | Required if the site is on Prime Farmland; pre- and post-construction soil sampling required. | Special Use Permit
Decommissioning Plan & Financial Security Bond | end-of-life planning | Plan for removal of system at end-of-life, including a financial bond (110-150% of removal cost). | Special Use Permit
Community Benefit Agreement | community impact | Developer may be required to provide payments or public improvements to offset project impacts. | Special Use Permit
Payment in Lieu of Taxes (PILOT) Agreement | taxation & financial impact | Negotiation with the town for tax payments in place of standard property taxes. | Special Use Permit & Tax Compliance
Building Permit | construction compliance | Ensures project meets NYS Building Code; must be approved before work begins. | Construction Permit
Electrical Permit | electrical compliance | Ensures project meets National Electric Code (NEC) for safe electrical interconnection. | Construction Permit
Interconnection Agreement | utility grid connection | Required before energization; must be signed with LIPA or another utility provider. | Construction Permit & Utility Approval
Fire Safety & Emergency Response Plan | public safety | Developer must coordinate with local fire departments and first responders. | Construction Permit
Insurance & Liability Coverage Report | risk management | Proof of liability insurance for damages, accidents, and infrastructure failures. | Construction Permit

## NY DG Interconnection Database
Utility | Step | Required? | Description | Description II | Permit Category | Typical Length (days) | Professional Certification
National Grid | Pre-Application | Optional |  |  |  | 10
$/sqft
43560 | 15 | 653400
Deeded Acres |  | $/acre
57.53 | 84700 | 1472.2754
70.29 | 61300 | 872.1013
62.44 | 69800 | 1117.8732
68.77 | 75000 | 1090.5919
83.39 | 53800 | 645.1613
58.2 | 62600 | 1075.6014
78.1 | 97500 | 1248.3995
77.19 | 90700 | 1175.0226
93.06 | 47100 | 506.1251
95.08 | 60800 | 639.4615
62.8 | 81860 | 1303.5032
59.3 | 72200 | 1217.538
57.89 | 68600 | 1185.0061
74.5 | 106500 | 1429.5302
78.9 | 80000 | 1013.9417
100.72 | 102700 | 1019.6584
66.58 | 200000 | 3003.905
83.8 | 125400 | 1496.42
79.53 | 70000 | 880.171
82.5 | 88200 | 1069.0909
60.22 | 83300 | 1383.2613
56.2 | 81200 | 1444.8398
75.41 | 96000 | 1273.0406
52.23 | 25800 | 493.969
81.51 | 81000 | 993.7431
86.39 | 47100 | 545.202
62.28 | 84500 | 1356.7759
77.55 | 99200 | 1279.1747
95.7 | 76700 | 801.4629
94 | 25800 | 274.4681
99.88 | 237000 | 2372.8475
| Lease average | 1107.323
| Option premium | 1328.7876

## Local Permitting Application Re
Requirement | Description | Cost | Permit Category
Special Use Permit Application Form | Official application form submitted to the Town Planning Board
Certified Public Notification Proof | Proof of notification sent to landowners within 200 feet (certified mail receipts)
Site Plan – Property Boundaries & Features | Must include a map showing roads, existing structures, water bodies, and adjacent properties
Site Plan – Solar Array Layout | Diagram showing the placement of panels, inverters, and other key equipment
Site Plan – Grading & Excavation Plan | Document showing elevation changes, cut/fill areas, and soil disturbance
Site Plan – Stormwater & Erosion Control Plan | Compliance with NYS DEC guidelines for managing runoff and preventing soil erosion
Site Plan – Vegetation Plan | Clearing and replanting details, including preservation of existing trees and new plantings
Site Plan – Utility Interconnection Plan | Diagram and documentation showing how the system connects to the electrical grid
Glare Mitigation Statement | Report proving panels have anti-reflective coatings and will not cause hazardous glare
Lighting Plan | Documentation of shielded, downcast lighting design to prevent light pollution
Security & Fencing Plan | Plan for a 7-ft security fence with self-locking gate per zoning requirements
Visual Impact Assessment | If the project is over 10 acres, must include viewshed analysis and landscaping plan
Landscaping Plan
Environmental Impact Assessment (SEQRA Review) | If required, must include a report on ecological impact and mitigation strategies
Prime Farmland Impact Study | Report detailing if the project affects Prime Farmland; if so, must prove <50% land usage
Pollinator-Friendly Vegetation Plan | Must document 20% of the project planted with native species
Decommissioning Plan | Plan detailing how the site will be restored and equipment removed at end of project life
Decommissioning Financial Security (Bond/Escrow) | 125% of removal cost posted in a financial security account
Operations & Maintenance Plan | Document outlining long-term system maintenance, vegetation control, and repairs
Equipment Specifications | Ensure compliance with zoning, electrical, and building codes.
Road Use Maintenance Agreement (RUMA) | Agreement detailing road use, maintenance responsibilities, and repairs due to construction traffic.
Socioeconomic Report | Assessment of project benefits, including tax revenue, job creation, and local economic impact.
Community Engagement Report | Documentation of outreach efforts, meetings, and community feedback.
Complaint Resolution Plan | Plan for handling community complaints related to construction and operation.
FAA Determination of No Hazard (DNH) | Federal Aviation Administration confirmation that the project does not pose hazards to air traffic.
Route Evaluation & Traffic Study | Analysis of transportation impacts, road conditions, and mitigation measures.
Noise Study | Evaluation of noise levels from inverters, transformers, and construction activities.
Geology & Hydrology Report | Assessment of soil conditions, groundwater impact, and subsurface geology.
Wetland Delineation Report | Identification and mapping of wetlands on or near the project site.
Ecological Assessment | Evaluation of habitat and wildlife impacts, including mitigation strategies.
HDD Inadvertent Return Contingency Plan | Plan to prevent and manage drilling fluid spills from horizontal directional drilling.
SHPO Concurrence | State Historic Preservation Office approval regarding historical site impacts.
Historic Resource Survey | Inventory of historical and culturally significant structures in the project area.
Phase 1 Archaeology Survey | Study determining if the project site contains any significant archaeological artifacts.
Visual Resource Assessment | Analysis of project visibility and aesthetic impacts from public viewpoints.
Landscape Plan | Aesthetic integration and screening using vegetation and natural barriers.
Emergency Response Plan | Site emergency protocols for fire, medical, and disaster response.
Drain Tile Assessment | Evaluation of subsurface drainage systems and potential impacts on agricultural land.
Unanticipated Discovery Plan | Plan for managing unexpected archaeological finds during construction.
EMF Exposure Study | Evaluates electromagnetic field safety | Confirms EMF levels ≤ 2 milligauss at boundaries | Construction Permit
Fire Safety & Emergency Plan | Ensures safe response to incidents | Requires first responder coordination and training | Construction Permit
Interconnection Agreement | Confirms grid compatibility | Agreement with LIPA or local utility provider | Construction Permit
Insurance & Liability Report | Provides financial risk protection | Proof of liability insurance coverage | Construction Permit
Environmental Impact Study (EIS) | Assesses overall environmental effects | SEQRA compliance, impact on land, water, air, traffic, and wildlife | Special Exception Approval
Wildlife & Habitat Study | Protects wildlife corridors and endangered species | Survey of affected species and mitigation strategies | Special Exception Approval
Stormwater Management Plan | Prevents runoff and erosion | SWPPP compliance, drainage system design | Special Exception Approval & Construction Permit
Wetlands & Aquifer Protection Study | Ensures groundwater and wetland protection | Identifies protected zones and contamination risks | Special Exception Approval
Clearing Calculations Survey | Determines land clearing impact | Required for parcels over 10 acres | Special Exception Approval
Traffic Impact Study | Evaluates construction and operational traffic | Identifies needed road improvements | Special Exception Approval
Substation & Infrastructure Plan | Determines grid compatibility and required upgrades | Assesses new poles, transformers, or substations | Special Exception Approval & Utility Interconnection
Decommissioning Plan & Bond | Ensures proper removal of system at project’s end | Includes cost estimate and financial bond | Special Exception Approval & Decommissioning Compliance
Glare & Reflection Study | Prevents hazardous solar glare | Assesses potential reflection impact | Special Exception Approval
Noise Compliance Study | Ensures compliance with noise ordinances | Measures inverter and transformer noise levels | Conditionally Required for Special Exception; Always Required for Construction Permit & Post-Construction Compliance
EMF Exposure Study | Evaluates electromagnetic field safety | Confirms EMF levels ≤ 2 milligauss at boundaries | Construction Permit & Post-Construction Compliance
Fire Safety & Emergency Plan | Ensures safe response to incidents | Requires first responder coordination and training | Construction Permit & Post-Construction Compliance
Interconnection Agreement | Confirms grid compatibility | Agreement with LIPA or local utility provider | Utility Interconnection Approval
Insurance & Liability Report | Provides financial risk protection | Proof of liability insurance coverage | Construction Permit
Site Plan Approval | Zoning & Planning | Layout, components, access, setbacks, landscaping, stormwater plans. | Special Use Permit
Special Use Permit Application | Land Use & Zoning | Required for all commercial-scale projects; includes environmental and zoning compliance studies. | Special Use Permit
Environmental Impact Study (EIS) | SEQRA Compliance | Analyzes environmental effects, including wetlands, habitat, noise, stormwater, and land use impacts. | Special Use Permit
Wildlife & Habitat Study | Environmental Compliance | Evaluates potential disruptions to local wildlife corridors and habitats. | Special Use Permit
Stormwater & Erosion Control Plan | Environmental Protection | Ensures proper drainage and erosion control measures are in place. | Special Use Permit & Construction Permit
Wetlands & Aquifer Protection Study | Water Resource Protection | Required if the project site is near protected wetlands or groundwater resources. | Special Use Permit
Clearing & Grading Plan | Land Use Compliance | Ensures compliance with land alteration rules, including tree removal and grading. | Special Use Permit & Construction Permit
Traffic Impact Study | Road Use & Public Safety | Assesses impact on local roads, school bus routes, and emergency access. | Special Use Permit
Road Use Agreement | Infrastructure Protection | Developer must repair town roads damaged by construction traffic; includes financial bond. | Special Use Permit & Pre-Construction Compliance
Substation & Infrastructure Plan | Utility Compliance | Required if grid interconnection necessitates upgrades (e.g., new substations, transmission lines). | Special Use Permit & Utility Interconnection
Noise Study | Community & Public Health | Evaluates anticipated noise levels from inverters, transformers, and construction activity. | Special Use Permit (conditionally required) & Construction Permit
Glare & Reflection Study | Traffic & Aviation Safety | Ensures no hazardous glare for roads, aircraft, or nearby properties. | Special Use Permit
Viewshed & Line-of-Sight Analysis | Aesthetic & Visual Impact | Provides scaled visual renderings of the solar project at installation, 5 years, and 10 years. | Special Use Permit
Soil Analysis & Pre-Development Conditions | Agricultural Land Protection | Required if the site is on Prime Farmland; pre- and post-construction soil sampling required. | Special Use Permit
Decommissioning Plan & Financial Security Bond | End-of-Life Planning | Plan for removal of system at end-of-life, including a financial bond (110-150% of removal cost). | Special Use Permit
Community Benefit Agreement | Community Impact | Developer may be required to provide payments or public improvements to offset project impacts. | Special Use Permit
Payment in Lieu of Taxes (PILOT) Agreement | Taxation & Financial Impact | Negotiation with the town for tax payments in place of standard property taxes. | Special Use Permit & Tax Compliance
Building Permit | Construction Compliance | Ensures project meets NYS Building Code; must be approved before work begins. | Construction Permit
Electrical Permit | Electrical Compliance | Ensures project meets National Electric Code (NEC) for safe electrical interconnection. | Construction Permit
Interconnection Agreement | Utility Grid Connection | Required before energization; must be signed with LIPA or another utility provider. | Construction Permit & Utility Approval
Fire Safety & Emergency Response Plan | Public Safety | Developer must coordinate with local fire departments and first responders. | Construction Permit
Insurance & Liability Coverage Report | Risk Management | Proof of liability insurance for damages, accidents, and infrastructure failures. | Construction Permit
Stormwater & Erosion Control Plan | Environmental Protection | Must be finalized before construction begins. | Construction Permit
Noise Study | Community & Public Health | Finalized noise study to confirm compliance with operational sound limits. | Construction Permit

## ALEX Local Permitting Applicati
Requirement | Description | Type of Work | Required | AHJ | Time Length | Duration Variability | Labor Time | Labor Costs | Application fee | Fixed Deadline | Pre-Requirements | Professional Engineer/Consultant Needed? | Automatable | Source
Special Use Permit Application Form | Official application form submitted to the Town Planning Board | Application Form | Yes | Township | <4 months | Fixed/variable | 30 hours | 5000 | $200-600 |  | Environmental Assessment Form, Site Plan |  |  | https://www.cityofrochester.gov/sites/default/files/migrated/WorkArea-DownloadAsset.aspx-id-21474848659.pdf | GZA and Colliers
Environmental Assessment Form | document used under the State Environmental Quality Review Act (SEQRA) to help state or local agencies evaluate the potential environmental impacts of a proposed project before making a decision. | Application Form | Yes | State |  | Variable | 1 | 1500 |  |  |  |  | Yes | https://dec.ny.gov/regulatory/permits-licenses/seqr/eaf-workbooks | https://dec.ny.gov/sites/default/files/2024-08/feafpart1.pdf
Site Plan Application Form |  | Application Form |  | Township |  | Variable | 30 hours | 5000
Signed Lease Agreement | A signed lease agreement with the landowner is required for a special use permit application | Documentation | Yes | Township | 3-6 months | Variable |  |  |  |  | Landowner engagement
Geotechnical Study/Report | Assessment of soil conditions, groundwater impact, and subsurface geology. | Study | Yes | Township | 3 months | Variable |  | 16000-26000 |  |  | Landowner engagement | Yes | No | Tony
Certified Public Notification Proof | Proof of notification sent to landowners within 200 feet (certified mail receipts) | Documentation | Yes | Township
Site Plan – Property Boundaries & Topological Features | Must include a map showing roads, existing structures, water bodies, and adjacent properties | Study | Yes | Township | 2 months | Variable |  | 13500 |  |  |  | Yes | Maybe
Site Plan – Solar Array Layout | Diagram showing the placement of panels, inverters, and other key equipment | Study | Yes | Township | 4 months | Variable |  | 45000 |  |  | Geotechnical study | Yes
Site Plan – Grading & Excavation Plan | Document showing elevation changes, cut/fill areas, and soil disturbance | Study | Yes | Township | 4 months | Variable | [5 empty] | Yes
Site Plan – Stormwater & Erosion Control Plan | Compliance with NYS DEC guidelines for managing runoff and preventing soil erosion | Study | Yes | Township | 4 months | Variable | [5 empty] | Yes
Site Plan – Vegetation Plan | Clearing and replanting details, including preservation of existing trees and new plantings | Study | If required (more than 3 trees need to be cut) | Township | 4 months | Variable | [5 empty] | Yes
Site Plan – Utility Interconnection Plan | Diagram and documentation showing how the system connects to the electrical grid | Study | Yes | Township | 4 months | Variable | [5 empty] | Yes
Site Plan -- Stormwater Pollution Prevention Plan | A Stormwater Pollution Prevention Plan (SWPPP) is a site-specific, written document developed to identify potential sources of stormwater pollution at a construction site or industrial facility | Study | Yes | Township | 4 months | Variable | [5 empty] | Yes
Preliminary Wetlands Assessment | Site visit to confirm the presence or absence of wetlands on the site. | Study | Yes |  | <1 month | Variable |  | 2750 | [5 empty] | GZA and Colliers
Wetlands, Aquifer, Wildlife Protection Study | Identifies protected zones and contamination risks | Study | If required |  | 3 months | Variable |  | 7800-9300 | [5 empty] | Colliers, GZA
State Pollutant Discharge Elimination System (SPDES) Notice of Intent | It comes with supporting documents such as a Stormwater Pollution Prevention Plan (SWPPP) and a Soil Erosion & Sediment Control Plan, which show how the project will manage stormwater and minimize erosion during construction. | Application Form | Yes | State | <1 month | Variable |  | 500 |  |  | Stormwater & Erosion Control Plan
Decommissioning Plan | Plan detailing how the site will be restored and equipment removed at end of project life. Can include restoration of soil areas, vegetation depending on the county. | Study | Yes | Township | <1 month | Variable | 10-20 hours | 1500-3000 | [5 empty] | http://www.townofcanandaigua.org/documents/files/County%20Road%2010%202890%202021-07-07%20DEcommissioning%20Plan.pdf
Decommissioning Agreement | Requires agreement between landowners, project developers, system operators | Documentation | Yes | Townshipp | 1-3 months | Fixed | 5-10 hours | 750-1500 |  |  | Financial Security
Decommissioning Financial Security (Bond/Escrow) | 110-150% of removal cost posted in a financial security account, or through a letter of credit. | Documentation | Yes | Township
Road Use Agreement/permit | Developer must repair town roads damaged by construction traffic; includes financial bond. | Documentation | Some AHJ | Township |  | Fixed | 12 hours | 2000
Traffic Impact Study | Assesses impact on local roads, school bus routes, and emergency access. | Study | If required | Township |  | Variable | 20-30 hours | 2600-3900 | [5 empty] | https://documents.dps.ny.gov/public/Common/ViewDoc.aspx?DocRefId=802c328d-0000-cd40-99d4-058f4d5c931d
Viewshed & Line-of-Sight Analysis (Visual Impact Assessment) | At a minimum, a line-of-sight profile analysis shall be provided. Depending upon the scope and potential significance of the visual impacts, additional impact analyses, including, for example, a digital viewshed report, may be required to be submitted by the applicant. | Study | If required (project is bigger than 10 acres) | Township | 4 months | Variable |  | 5000-20000 | [5 empty] | https://www.eagleeyedesign.co.uk/how-much-does-an-lvia-cost#:~:text=Project%20Size%20and%20Complexity,numerous%20viewpoints%2C%20&%20advanced%20visualisations.
Screening and Landscaping Plan | to show adequate measures to screen through landscaping, grading, or other means so that views of Solar Panels and Solar Energy Equipment shall be minimized as reasonably practical from public roadways and adjacent properties to the extent feasible. | Study | If required (project is bigger than 10 acres) | Township | 1 month | Variable | 8 hours | 1000 |  |  |  |  | Maybe
Noise Study | Evaluation of noise levels from inverters, transformers, and construction activities. | Study | Some AHJ | Township | 1 month | Variable | 11 hours | 1540 |  |  |  |  | No
Glare & Reflection Study | Ensures no hazardous glare for roads, aircraft, or nearby properties. | Study | Some AHJ | Township | 1 month | Variable | 8 hours | 1120 |  |  |  |  | Maybe
Operations & Maintenance Plan | Document outlining long-term system maintenance, vegetation control, and repairs | Study | Yes | Township | < 1 month | Variable | 4 hours | 480 | [5 empty] | https://mccmeetingspublic.blob.core.usgovcloudapi.net/lansingny-meet-8e9e613ac40e4bef831cdee66b724566/ITEM-Attachment-001-636b7f97cf2a4191ab35c9bfdfbd2f1a.pdf#:~:text=3,once%20per%20month%2C%20or%20as
Phase I Environmental Site Assessment (SEQRA Review) | Based on the environmental assessment form, a committee will decide whether this is required. If required, must include a report on ecological impact and mitigation strategies. 4500 for labor costs, 1000 for travel, equipment, etc | Study | If required | SEQRA | < 1 month | Variable |  | 4000-5500
Native Vegetation Plan | Must implement, and maintain native vegetation to the extent practicable pursuant to a vegetation management plan by providing native perennial vegetation and foraging habitat beneficial to game birds, songbirds, and pollinators. | Study | If required (on agricultural land)
Coordinated Electric System Interconnection Review (CESIR) |  |  | Yes | Township
Community Engagement Report | Documentation of outreach efforts, meetings, and community feedback. | Documentation | Some AHJ | Township
Complaint Resolution Plan | Plan for handling community complaints related to construction and operation. |  | Some AHJ
FAA Determination of No Hazard (DNH) | Federal Aviation Administration confirmation that the project does not pose hazards to air traffic. | Documentation | Some AHJ | Federal |  | Fixed | 4 | 500 |  |  |  |  | Maybe | GZA, Environmental permitting
Structural Archeological Assessment Form | Inventory of historical and culturally significant structures in the project area. Obtain written confirmation of determination from the NYS State Office of Historic Preservation; |  | Some AHJ |  | 6-8 weeks | Fixed | 10 | 1000 | [5 empty] | https://www.nysl.nysed.gov/libdev/construc/shpo.htm | https://extapps.dec.ny.gov/docs/permits_ej_operations_pdf/shpaapplguide.pdf | https://extapps.dec.ny.gov/docs/permits_ej_operations_pdf/saaf.pdf
Stage 1 Archaeology Survey | Study determining if the project site contains any significant archaeological artifacts, both through literature research and fieldwork |  | If required
Emergency Response Plan | Site emergency protocols for fire, medical, and disaster response. |  | Some AHJ
Construction Plan |  |  | Some AHJ
Agricultural Impact Statement | Statement to determine the impact of the project on agriculture in the township. | Documentation | If required (project > 5MW) and only in some AHJ |  |  |  | 2025-04-08 | 500
Insurance & Liability Proof | Proof of liability insurance coverage | Documentation | Some AHJ |  |  | Fixed | [7 empty] | https://locallaws.dos.ny.gov/sites/default/files/drop_laws_here/ECMMDIS_appid_DOS20230109123423/Content/090213438031d8f1.pdf#:~:text=i,A
Community Benefit Agreement | Developer may be required to provide payments or public improvements to offset project impacts. A common type of community benefit is often the PILOT program | Documentation | Some AHJ
Payment in Lieu of Taxes (PILOT) Agreement | Negotiation with the town for tax payments in place of standard property taxes. | Documentation | Some AHJ |  | 2-4 months | Fixed |  |  | TBD
Building Permit | Ensures project meets NYS Building Code; must be approved before work begins. | Application Form | Yes | State |  | Fixed |  | 500 | $200 / 1000 sq ft |  |  | Yes | Maybe | https://dos.ny.gov/system/files/documents/2023/07/0301-f.pdf | https://dos.ny.gov/system/files/documents/2022/12/dos-admin-and-enforcement-fee-schedule-2022-08.pdf
Electrical Permit | Ensures project meets National Electric Code (NEC) for safe electrical interconnection. | Application Form | Yes | State |  | Fixed |  | 500
Public Hearings |  | Meeting | Yes | Township | 4 months | Fixed | 40 | 10000
Total Estimated Costs Best Case (Lower Estimate) | 109140
Total Estimated Costs Best Case (Upper Estimate) | 120390
Total Estimated Costs Worst Case (Lower Estimate) | 130040
Total Estimated Costs Worst Case (Upper Estimate) | 140590
109140
130040
140590
Design Requirements
Security & Fencing Plan | Plan for a 7-ft security fence with self-locking gate per zoning requirements
Equipment Specifications | Ensure compliance with zoning, electrical, and building codes. |  | Yes
Glare Mitigation Statement | Report proving panels have anti-reflective coatings and will not cause hazardous glare
Lighting Plan | Documentation of shielded, downcast lighting design to prevent light pollution
rare
Drain Tile Assessment | Evaluation of subsurface drainage systems and potential impacts on agricultural land.
Unanticipated Discovery Plan | Plan for managing unexpected archaeological finds during construction.
EMF Exposure Study | Confirms EMF levels ≤ 2 milligauss at boundaries
Soil Analysis & Pre-Development Conditions | Required if the site is on Prime Farmland; pre- and post-construction soil sampling required. Part of geotechnical study typically?
Townships Covered
Town of Springwater
Arcadia
Meredith | [13 empty] | https://locallaws.dos.ny.gov/sites/default/files/drop_laws_here/ECMMDIS_appid_DOS20230109123423/Content/090213438031d8f1.pdf#:~:text=i,A